## 📊 Dashboard
IDEA INTERNAL PORTAL — TASK MANAGEMENT
Development Backlog & Sprint Planning
Total Tasks |  | Epics |  | Phase 1 |  | Phase 2 |  | Phase 3 | Phase 4
200 |  | 25 |  | 66 |  | 64 |  | 44 | 26
PHASE SUMMARY
Phase | Name | Description | Epics | Tasks | Story Pts
PH1 | Phase 1 — Foundation | Auth, Core Data, Operation (Hiring + Payroll + Onboarding) | 6 | 61 | 342
PH2 | Phase 2 — Core Operations | Technology Dept, Finance Dept, Global Self-Service, Outsource | 7 | 63 | 377
PH3 | Phase 3 — Growth | Sales & Marketing, SP Automation, Executive Portal, Content | 7 | 42 | 226
PH4 | Phase 4 — Intelligence | AI Features, Advanced Analytics, Digital Signature, Reports | 5 | 26 | 201
EPIC BREAKDOWN
Epic ID | Epic Name | Phase | Tasks | Story Pts | Critical | High | Med
EP-01 | Authentication & Authorization | PH1 | 12 | 71 | 0 | 0 | 0
EP-02 | Employee & Organization Master Data | PH1 | 16 | 86 | 0 | 0 | 0
EP-03 | Hiring & Recruitment | PH1 | 10 | 57 | 0 | 0 | 0
EP-04 | Onboarding Management | PH1 | 7 | 37 | 0 | 0 | 0
EP-05 | Payroll Processing | PH1 | 11 | 62 | 0 | 0 | 0
EP-06 | Notification Engine | PH1 | 5 | 29 | 0 | 0 | 0
EP-07 | Project Management | PH2 | 15 | 102 | 0 | 0 | 0
EP-08 | Employee Assessment & OKR | PH2 | 10 | 55 | 0 | 0 | 0
EP-09 | Finance & Accounting | PH2 | 13 | 82 | 0 | 0 | 0
EP-10 | Outsource Placement & Timesheet | PH2 | 11 | 65 | 0 | 0 | 0
EP-11 | Leave & Attendance | PH2 | 6 | 34 | 0 | 0 | 0
EP-12 | Reimbursement | PH2 | 4 | 18 | 0 | 0 | 0
EP-13 | Procurement & Asset Register | PH2 | 4 | 21 | 0 | 0 | 0
EP-14 | Sales Leads & Funnel | PH3 | 9 | 46 | 0 | 0 | 0
EP-15 | Proposal Management | PH3 | 5 | 29 | 0 | 0 | 0
EP-16 | Sales Targets & Reports | PH3 | 5 | 29 | 0 | 0 | 0
EP-17 | Warning Letter (SP) System | PH3 | 6 | 29 | 0 | 0 | 0
EP-18 | Executive Portal | PH3 | 6 | 41 | 0 | 0 | 0
EP-19 | Broadcast, Events & Company Info | PH3 | 5 | 28 | 0 | 0 | 0
EP-20 | Resignation & Offboarding | PH3 | 6 | 24 | 0 | 0 | 0
EP-21 | AI Action Items & SP Drafting | PH4 | 4 | 29 | 0 | 0 | 0
EP-22 | Digital Signature (BA & SP) | PH4 | 5 | 36 | 0 | 0 | 0
EP-23 | AI Executive Summary | PH4 | 5 | 39 | 0 | 0 | 0
EP-24 | Data Migration & Import Tools | PH4 | 6 | 50 | 0 | 0 | 0
EP-25 | Reporting & Analytics | PH4 | 6 | 47 | 0 | 0 | 0

## 📋 All Tasks
IDEA INTERNAL PORTAL — COMPLETE TASK BACKLOG
Task ID | Epic ID | Epic Name | Phase | Type | Title | Description | Priority | Story Pts | Dependencies | Role | Status | Completion Note
TSK-001 | EP-01 | Authentication & Authorization | PH1 | Story | Single Login Portal Setup | Create unified login page at portal.ide.asia with company branding | Critical | 8 |  | BE+FE | Done | M1.1 — Single Login Portal
TSK-002 | EP-01 | Authentication & Authorization | PH1 | Task | JWT Authentication Implementation | Implement JWT token-based auth with refresh token mechanism | Critical | 5 | TSK-001 | BE | Done | M1.1 — JWT auth + refresh token rotation
TSK-003 | EP-01 | Authentication & Authorization | PH1 | Task | Role-Based Access Control (RBAC) Engine | Build RBAC middleware; map Level 1-6 to permission sets | Critical | 8 | TSK-002 | BE | Done | M1.1 — RBAC engine + Resource×Action enum
TSK-004 | EP-01 | Authentication & Authorization | PH1 | Task | Permission Matrix Implementation | Implement all 12 permission matrix rules per module per role | Critical | 13 | TSK-003 | BE | Done | M1.1 — Permission Matrix UI (Executive only)
TSK-005 | EP-01 | Authentication & Authorization | PH1 | Task | Session Management & Auto-logout | Session timeout, concurrent session control, auto-save drafts on timeout | High | 5 | TSK-002 | BE | Done | M1.1 — Session mgmt + Redis blacklist + broadcast logout
TSK-006 | EP-01 | Authentication & Authorization | PH1 | Task | Account Lock After Failed Attempts | Lock account after 5 failed logins; 30-min timeout; admin unlock | High | 3 | TSK-002 | BE | Done | M1.1 — Account lock after failed login attempts
TSK-007 | EP-01 | Authentication & Authorization | PH1 | Task | Password Reset Flow | Forgot password flow via email OTP | Medium | 3 | TSK-001 | BE+FE | Done | M1.1 — Forgot password + reset via token
TSK-008 | EP-01 | Authentication & Authorization | PH1 | Task | Dark Mode & Accessibility Settings | Toggle dark/light mode; font size control; contrast settings | Medium | 5 | TSK-001 | FE | Done | M1.1 — Settings page (theme, font, BFA toggle)
TSK-009 | EP-01 | Authentication & Authorization | PH1 | Task | Mobile Responsive Layout Framework | Setup responsive grid; breakpoints for mobile/tablet/desktop | Critical | 8 | TSK-001 | FE | Done | M1.1 — Mobile responsive AppShell (Sider + Drawer)
TSK-010 | EP-01 | Authentication & Authorization | PH1 | Sub-task | Login Page UI | Design and build login page with company logo, responsive layout | High | 3 | TSK-001 | FE | Done | M1.1 — LoginPage UI dengan NIK login
TSK-011 | EP-01 | Authentication & Authorization | PH1 | Sub-task | Audit Trail Logger | Log all critical actions: who, what, when, IP address | High | 5 | TSK-003 | BE | Done | M1.1 — AuditLog model + audit_log() helper, persona name eksplisit
TSK-012 | EP-01 | Authentication & Authorization | PH1 | Sub-task | Global Search (Employee & Project) | Search bar in header; search employees and projects across system | Medium | 5 | TSK-004 | BE+FE | Done | M1.1 — GlobalSearch Cmd+K (Employee + Project)
TSK-013 | EP-02 | Employee & Organization Master Data | PH1 | Story | Employee Master Data Module | CRUD for all employee data including PKWT/PKWTT, Type A/B/C | Critical | 13 | TSK-003 | BE+FE | Done | M1.2 — Employee CRUD + bulk import + filter
TSK-014 | EP-02 | Employee & Organization Master Data | PH1 | Task | Employee Profile Form | All fields: identity, contact, bank, BPJS, employment details | Critical | 8 | TSK-013 | FE | Done | M1.2 — EmployeeCreatePage form + EmployeeDetailPage tabs
TSK-015 | EP-02 | Employee & Organization Master Data | PH1 | Task | Organization Hierarchy Tree | Tree data structure for parent-child reporting; circular reference validation | Critical | 8 | TSK-013 | BE | Done | M1.2 — OrgChartPage tree visualization
TSK-016 | EP-02 | Employee & Organization Master Data | PH1 | Task | Department & Level Management | CRUD for departments; level 1-6 configuration per dept | Critical | 5 | TSK-013 | BE+FE | Done | M1.2 — Department + Position CRUD
TSK-017 | EP-02 | Employee & Organization Master Data | PH1 | Task | Salary Range Configuration per Level | Set min/max salary range per level; used for promotion suggestion | High | 3 | TSK-016 | BE+FE | Done
TSK-018 | EP-02 | Employee & Organization Master Data | PH1 | Task | BPJS Configuration per Employee | Configure BPJS Kesehatan & Ketenagakerjaan split per employee/level | Critical | 5 | TSK-013 | BE+FE | Done | M1.2 — BPJS fields di Employee + Contract
TSK-019 | EP-02 | Employee & Organization Master Data | PH1 | Task | Employee Status Management | Status: Active, Probation, On Leave, Terminated, Resigned; auto-access revoke | Critical | 5 | TSK-013 | BE | Done | M1.2 — Employee status lifecycle (PROBATION/ACTIVE/...)
TSK-020 | EP-02 | Employee & Organization Master Data | PH1 | Task | PKWT Contract Tracking | Store contract start/end date; alert H-30 and H-7 to supervisor + Operation | High | 5 | TSK-013 | BE | Done | M1.2 — ContractsListPage — PKWT/PKWTT tracking + expiry
TSK-021 | EP-02 | Employee & Organization Master Data | PH1 | Task | Mutation (Department Transfer) Flow | Transfer employee between depts; preserve history; notify PM if in project | High | 5 | TSK-015 | BE+FE | Done
TSK-022 | EP-02 | Employee & Organization Master Data | PH1 | Task | Promotion Flow | Change level; suggest salary range; set effective date; audit trail | High | 5 | TSK-017 | BE+FE | Done
TSK-023 | EP-02 | Employee & Organization Master Data | PH1 | Task | Employee Reactivation | Re-activate former employee; restore all history; re-onboard flow | Medium | 3 | TSK-019 | BE+FE | Done
TSK-024 | EP-02 | Employee & Organization Master Data | PH1 | Task | Org Chart Auto-generation | Visual org chart from hierarchy data; tree + list view; all employees | High | 8 | TSK-015 | FE | Done | M1.2 — OrgChartPage auto-build dari Department + Employee
TSK-025 | EP-02 | Employee & Organization Master Data | PH1 | Sub-task | Employee List & Filter View | Filterable employee list: by dept, level, status, type | High | 3 | TSK-013 | FE | Done | M1.2 — EmployeeListPage dengan filter + pagination
TSK-026 | EP-02 | Employee & Organization Master Data | PH1 | Sub-task | Work Calendar Management | Set working days, holidays, dept override; affects payroll & leave | Critical | 5 | TSK-016 | BE+FE | Done | M1.2 — WorkCalendar + Holiday model
TSK-027 | EP-02 | Employee & Organization Master Data | PH1 | Sub-task | Vendor List Management | CRUD vendor: name, contact, category; used in procurement | Medium | 2 | TSK-013 | BE+FE | Done | M1.2 — Vendor model + CRUD endpoint (TSK-023)
TSK-028 | EP-02 | Employee & Organization Master Data | PH1 | Sub-task | Client Master Data | CRUD client: company, PIC, contract details; linked to outsource & project | Critical | 3 | TSK-013 | BE+FE | Done | M1.2 — Client model di Organization domain
TSK-029 | EP-03 | Hiring & Recruitment | PH1 | Story | Hiring Request Workflow | End-to-end hiring request: submit → 2-layer approval → Operation receives | Critical | 8 | TSK-004 | BE+FE | Done | M1.3 — JobOpening + JobApplication models + approval flow
TSK-030 | EP-03 | Hiring & Recruitment | PH1 | Task | Hiring Request Form | Fields: position, level, dept, reason (new/replacement), target date, description | Critical | 5 | TSK-029 | FE | Done | M1.3 — JobOpeningCreatePage form
TSK-031 | EP-03 | Hiring & Recruitment | PH1 | Task | 2-Layer Approval Engine (Generic) | Reusable approval component: Layer1 (supervisor) → Layer2 (GM/CLevel) | Critical | 8 | TSK-003 | BE | Done | M1.3 — Generic 2-layer approval pattern (leave/reimb/proc/sep/hiring)
TSK-032 | EP-03 | Hiring & Recruitment | PH1 | Task | Candidate Management | Add candidates: name, contact, CV upload, source; link to hiring request | Critical | 8 | TSK-029 | BE+FE | Done | M1.3 — Candidate stages: APPLIED → INTERVIEW → OFFERED → HIRED/REJECTED
TSK-033 | EP-03 | Hiring & Recruitment | PH1 | Task | Selection Stage Configuration | Configure stages per position; record Pass/Fail + notes per stage | High | 5 | TSK-032 | BE+FE | Done | M1.3 — JobOpening stages config
TSK-034 | EP-03 | Hiring & Recruitment | PH1 | Task | Offering Letter Generation | Generate offering letter PDF; fields: position, salary, start date; approval required | Critical | 8 | TSK-033 | BE+FE | Done
TSK-035 | EP-03 | Hiring & Recruitment | PH1 | Task | Candidate Status Tracking | Track: Screening → Interview → Offering → Hired / Rejected | High | 5 | TSK-032 | BE+FE | Done | M1.3 — Candidate status tracking + filter
TSK-036 | EP-03 | Hiring & Recruitment | PH1 | Task | Internal Job Board | Display approved job openings; visible to all employees | Medium | 3 | TSK-029 | FE | Done
TSK-037 | EP-03 | Hiring & Recruitment | PH1 | Sub-task | Duplicate Request Detection | Warn if similar position already requested in same month | Medium | 2 | TSK-029 | BE | Done
TSK-038 | EP-03 | Hiring & Recruitment | PH1 | Sub-task | Hiring Dashboard for Operation | View all open requests, pipeline status, fill rate metrics | High | 5 | TSK-029 | FE | Done | M1.3 — JobOpeningListPage dashboard
TSK-039 | EP-04 | Onboarding Management | PH1 | Story | Automated Onboarding Checklist | Auto-create checklist when candidate status = Hired; track completion | Critical | 8 | TSK-035 | BE+FE | Done | M1.3 — Onboarding template + auto-checklist generation
TSK-040 | EP-04 | Onboarding Management | PH1 | Task | Welcome Page for New Employees | Show welcome banner with text, images, handbook links on first login | High | 5 | TSK-039 | FE | Done
TSK-041 | EP-04 | Onboarding Management | PH1 | Task | Onboarding Checklist Items | Configurable checklist: contract signing, data entry, asset receipt, orientation | High | 5 | TSK-039 | BE+FE | Done | M1.3 — OnboardingTask items + completion tracking
TSK-042 | EP-04 | Onboarding Management | PH1 | Task | H-3 Pre-join Preparation Alert | Auto-alert Operation H-3 before join date to prepare accounts and assets | High | 3 | TSK-039 | BE | Done
TSK-043 | EP-04 | Onboarding Management | PH1 | Task | Account Activation on Join Date | Auto-activate employee account on join date; send login credentials | Critical | 3 | TSK-039 | BE | Done
TSK-044 | EP-04 | Onboarding Management | PH1 | Task | Probation Assessment Flow | Separate assessment form for Month 1, 2, 3 of probation; extend/pass/fail | High | 8 | TSK-039 | BE+FE | Done
TSK-045 | EP-04 | Onboarding Management | PH1 | Sub-task | Company Info Portal (CMS) | Operation manages: visi/misi, policies, SOP, handbook, templates; searchable | High | 5 | TSK-039 | BE+FE | Done
TSK-046 | EP-05 | Payroll Processing | PH1 | Story | Payroll Component Configuration | Setup fixed & variable salary components; BPJS; custom deductions per employee | Critical | 8 | TSK-018 | BE+FE | Done
TSK-047 | EP-05 | Payroll Processing | PH1 | Task | Monthly Attendance Input by Operation | Operation inputs total working days + overtime per employee before cutoff | Critical | 5 | TSK-046 | BE+FE | Done
TSK-048 | EP-05 | Payroll Processing | PH1 | Task | Payroll Calculation Engine | Calculate: gross = fixed + variable + OT; net = gross - BPJS - PPh21 - deductions | Critical | 13 | TSK-046 | BE | Done
TSK-049 | EP-05 | Payroll Processing | PH1 | Task | PPh 21 Manual Input per Employee | Finance inputs PPh21 amount per employee; stored as deduction component | Critical | 5 | TSK-048 | BE+FE | Done
TSK-050 | EP-05 | Payroll Processing | PH1 | Task | Payroll Review & Approval by GM/CLevel | Payroll summary review screen; approval required before processing | Critical | 5 | TSK-048 | BE+FE | Done
TSK-051 | EP-05 | Payroll Processing | PH1 | Task | Pay Slip Generation (PDF) | Generate individual pay slip PDF; all components itemized; publish to portal | Critical | 8 | TSK-050 | BE+FE | Done
TSK-052 | EP-05 | Payroll Processing | PH1 | Task | Pay Slip History Access | Employee views all pay slips since joining; download as PDF | Critical | 3 | TSK-051 | FE | Done
TSK-053 | EP-05 | Payroll Processing | PH1 | Task | THR Processing Module | Configure THR components; calculate prorated for <1yr; separate payment flow | High | 5 | TSK-048 | BE+FE | Done
TSK-054 | EP-05 | Payroll Processing | PH1 | Task | Prorated Final Payroll (Exit) | Calculate prorated salary on exit based on effective working days | Critical | 5 | TSK-048 | BE | Done
TSK-055 | EP-05 | Payroll Processing | PH1 | Sub-task | Payroll Period Configuration | Set payroll cutoff and disbursement dates; configurable per period | High | 3 | TSK-046 | BE+FE | Done
TSK-056 | EP-05 | Payroll Processing | PH1 | Sub-task | Payroll Duplicate Prevention | Block second submission for same employee in same period | Critical | 2 | TSK-047 | BE | Done
TSK-057 | EP-06 | Notification Engine | PH1 | Story | In-App Notification System | Real-time in-app notifications; notification bell; read/unread state | Critical | 8 | TSK-001 | BE+FE | Done
TSK-058 | EP-06 | Notification Engine | PH1 | Task | Notification Templates | Template per event: approval request, alert, deadline, system message | High | 5 | TSK-057 | BE | Done
TSK-059 | EP-06 | Notification Engine | PH1 | Task | Alert Rules Engine | Configure: PKWT H-30/H-7, contract renewal H-30/H-7, task H-3/H-1, payroll | High | 8 | TSK-057 | BE | Done
TSK-060 | EP-06 | Notification Engine | PH1 | Task | Approval Chain Notifications | Notify correct approver at each layer; escalate if approver inactive | Critical | 5 | TSK-031 | BE | Done
TSK-061 | EP-06 | Notification Engine | PH1 | Sub-task | Notification Retry & Failure Handling | Retry failed notifications; log failures; escalate to admin after 3 retries | Medium | 3 | TSK-057 | BE | Done
TSK-062 | EP-07 | Project Management | PH2 | Story | Project CRUD & Configuration | Create/edit projects: Client, Internal, R&D types; link to Sales deal or Direktur | Critical | 8 | TSK-028 | BE+FE | Done | M2.1 (CLAUDE.md TSK-022) — Project CRUD + members
TSK-063 | EP-07 | Project Management | PH2 | Task | Project Team Assignment | Assign PM + members; set role & allocation %; over-allocation warning | High | 5 | TSK-062 | BE+FE | Done | M2.1 — ProjectMember + allocation_pct
TSK-064 | EP-07 | Project Management | PH2 | Task | Kanban Board | Columns: Backlog/In Progress/Review/Done; drag-drop; task detail modal | Critical | 13 | TSK-062 | FE | Done | M2.1 (TSK-022 + TSK-022B) — Kanban board, informatif card di TSK-022B
TSK-065 | EP-07 | Project Management | PH2 | Task | Gantt Chart View | Timeline view of milestones & tasks; dependency lines; progress % | High | 13 | TSK-062 | FE | Done
TSK-066 | EP-07 | Project Management | PH2 | Task | Task Management | CRUD tasks: title, description, assignee, deadline, priority, milestone link | Critical | 8 | TSK-064 | BE+FE | Done | M2.1 — Task CRUD + status + assignee + slug Jira-style
TSK-067 | EP-07 | Project Management | PH2 | Task | Milestone Management | CRUD milestones; auto-calculate progress from tasks; block completion if open tasks | High | 5 | TSK-066 | BE+FE | Done | M2.1 → TSK-022B — Milestone replaced by Phase (4-level hierarchy)
TSK-068 | EP-07 | Project Management | PH2 | Task | Technical Documentation Module | Folder structure; file upload with versioning; project-member-only access | High | 8 | TSK-062 | BE+FE | Done
TSK-069 | EP-07 | Project Management | PH2 | Task | Project Closing Flow | Closing report form; client sign-off upload; approval; Finance + Sales notif | High | 8 | TSK-067 | BE+FE | Done | M2.1 — Project close flow + Direktur override
TSK-070 | EP-07 | Project Management | PH2 | Task | Change Request (CR) Module | CR form: scope/timeline/cost impact; approval; trigger Sales + Finance update | High | 5 | TSK-062 | BE+FE | Done
TSK-071 | EP-07 | Project Management | PH2 | Task | Internal Project Approval (Direktur) | Internal project requires Direktur approval; man-hour tracking; no billing | High | 5 | TSK-062 | BE+FE | To Do
TSK-072 | EP-07 | Project Management | PH2 | Task | Sub-contractor in Project | Add external sub-contractor as project member; link cost to Finance | Medium | 5 | TSK-063 | BE+FE | To Do
TSK-073 | EP-07 | Project Management | PH2 | Task | Jira Import Tool | Import existing projects from Jira JSON/CSV; map to system entities | High | 8 | TSK-062 | BE | To Do
TSK-074 | EP-07 | Project Management | PH2 | Sub-task | Project Status Management | Status flow: Draft/Active/On Hold/Completed/Terminated; Direktur override | Critical | 3 | TSK-062 | BE | Done | M2.1 — Project lifecycle DRAFT/ACTIVE/ON_HOLD/COMPLETED/TERMINATED
TSK-075 | EP-07 | Project Management | PH2 | Sub-task | Task Deadline Notifications | H-3 and H-1 alerts to assignee and PM; overdue flag | High | 3 | TSK-066 | BE | Done
TSK-076 | EP-07 | Project Management | PH2 | Sub-task | Project Report per Employee | Summary: projects, contribution, history; export PDF; access by level | High | 5 | TSK-062 | BE+FE | To Do
TSK-077 | EP-08 | Employee Assessment & OKR | PH2 | Story | OKR Framework Setup | Quarterly OKR: supervisor sets Objectives + Key Results; bulanan evaluasi | Critical | 8 | TSK-016 | BE+FE | Done | M2.1 (CLAUDE.md TSK-021) — OKR objectives + key results
TSK-078 | EP-08 | Employee Assessment & OKR | PH2 | Task | Monthly Assessment Form | Input OKR progress % + weighted scores; auto-calculate final score | Critical | 8 | TSK-077 | BE+FE | Done | M2.1 — Assessment form per period
TSK-079 | EP-08 | Employee Assessment & OKR | PH2 | Task | Assessment Weight Configuration | GM/CLevel configure OKR weight vs Weighted Score weight per dept | High | 3 | TSK-078 | BE+FE | Done | M2.1 — Assessment weight config per dept
TSK-080 | EP-08 | Employee Assessment & OKR | PH2 | Task | Performance Score Calculation Engine | Final Score = (OKR × weight%) + (Weighted × weight%); threshold logic | Critical | 8 | TSK-078 | BE | Done | M2.1 — Score calc (OKR + weighted) → final score
TSK-081 | EP-08 | Employee Assessment & OKR | PH2 | Task | SP Threshold Flag System | Month 1 <60: yellow; Month 2: orange; Month 3: auto-trigger SP to Operation | Critical | 5 | TSK-080 | BE | Done | M2.1 — SP threshold flag (kuning→oranye→merah→SP auto)
TSK-082 | EP-08 | Employee Assessment & OKR | PH2 | Task | Rating History View | Employee views all ratings since joining; trend graph; per-dept history preserved | High | 5 | TSK-078 | FE | Done | M2.1 — PerformancePage history tab
TSK-083 | EP-08 | Employee Assessment & OKR | PH2 | Task | Sales OKR Auto-pull | Auto-populate win rate & revenue actual from Sales module into OKR | High | 5 | TSK-077 | BE | To Do
TSK-084 | EP-08 | Employee Assessment & OKR | PH2 | Task | 360-Degree Feedback Module | Optional per dept; peers input feedback; separate from official rating | Medium | 8 | TSK-078 | BE+FE | To Do
TSK-085 | EP-08 | Employee Assessment & OKR | PH2 | Sub-task | Late Assessment Flagging | Flag late submissions; notify GM/CLevel; still accepted with flag | Medium | 2 | TSK-078 | BE | To Do
TSK-086 | EP-08 | Employee Assessment & OKR | PH2 | Sub-task | Assessment Leave Skip Logic | Skip assessment months for employees on extended approved leave | Critical | 3 | TSK-081 | BE | To Do
TSK-087 | EP-09 | Finance & Accounting | PH2 | Story | Chart of Accounts (CoA) Module | Import existing CoA; CRUD; mandatory mapping for all transactions | Critical | 8 | TSK-028 | BE+FE | To Do
TSK-088 | EP-09 | Finance & Accounting | PH2 | Task | Daily Transaction Input | Accrual basis; multi-currency; CoA mapping; attach document; status flow | Critical | 8 | TSK-087 | BE+FE | To Do
TSK-089 | EP-09 | Finance & Accounting | PH2 | Task | Multi-Currency Engine | Store original currency + exchange rate + IDR equivalent; IDR as functional | Critical | 8 | TSK-088 | BE | To Do
TSK-090 | EP-09 | Finance & Accounting | PH2 | Task | Transaction Reversal | Create reversal entry for posted transactions; cannot edit posted | Critical | 5 | TSK-088 | BE+FE | To Do
TSK-091 | EP-09 | Finance & Accounting | PH2 | Task | P&L Report Generation | Filter by period; breakdown by dept & revenue stream; comparison MoM/YoY | Critical | 8 | TSK-087 | BE+FE | To Do
TSK-092 | EP-09 | Finance & Accounting | PH2 | Task | Balance Sheet Generation | As-of-date snapshot; auto-validate assets = liabilities + equity | High | 8 | TSK-087 | BE+FE | To Do
TSK-093 | EP-09 | Finance & Accounting | PH2 | Task | Cash Flow Statement | Operating/Investing/Financing cash flow; period filter | High | 8 | TSK-087 | BE+FE | To Do
TSK-094 | EP-09 | Finance & Accounting | PH2 | Task | PPh 21 Monthly Recap | Auto-aggregate PPh21 inputs from payroll; export for manual reporting | High | 5 | TSK-049 | BE+FE | To Do
TSK-095 | EP-09 | Finance & Accounting | PH2 | Task | PPN Recap Module | Tag transactions as PPN-applicable; monthly recap; export for manual SPT | High | 5 | TSK-088 | BE+FE | To Do
TSK-096 | EP-09 | Finance & Accounting | PH2 | Task | Invoice Tracking | Manual invoice number input; link to project/outsource; status tracking; alerts | Critical | 8 | TSK-088 | BE+FE | Done | M2.2 (TSK-022C+D) — Invoice CRUD di app/finance + UI aging bucket
TSK-097 | EP-09 | Finance & Accounting | PH2 | Task | Invoice Overdue Alerts | Auto-alert at H+7, H+14, H+30 from due date; show in Executive dashboard | High | 3 | TSK-096 | BE | Done | M2.2 (TSK-022D) — Aging bucket coloring (CURRENT/1-30/31-60/61-90/90+)
TSK-098 | EP-09 | Finance & Accounting | PH2 | Task | Report Export (PDF + Excel) | Export all financial reports as PDF and Excel; chart included in PDF | High | 5 | TSK-091 | BE+FE | To Do
TSK-099 | EP-09 | Finance & Accounting | PH2 | Sub-task | Duplicate Transaction Detection | Warn on same amount+date+CoA+description combination | High | 3 | TSK-088 | BE | To Do
TSK-100 | EP-10 | Outsource Placement & Timesheet | PH2 | Story | Outsource Placement Management | CRUD placement: employee, client, position, dates, rate, billing type | Critical | 8 | TSK-028 | BE+FE | Done
TSK-101 | EP-10 | Outsource Placement & Timesheet | PH2 | Task | Multi-Client Placement Support | One employee → multiple simultaneous placements; allocation split | High | 5 | TSK-100 | BE+FE | To Do
TSK-102 | EP-10 | Outsource Placement & Timesheet | PH2 | Task | Billing Configuration per Client | Toggle: flat monthly OR per-timesheet; rate input; amandemen support | Critical | 5 | TSK-100 | BE+FE | To Do
TSK-103 | EP-10 | Outsource Placement & Timesheet | PH2 | Task | Monthly Timesheet Submission | Employee submits timesheet: daily attendance, absence, overtime per client | Critical | 8 | TSK-100 | BE+FE | Done
TSK-104 | EP-10 | Outsource Placement & Timesheet | PH2 | Task | Timesheet Approval by Operation | Operation review/approve/reject timesheet; rejection returns to employee | Critical | 5 | TSK-103 | BE+FE | Done
TSK-105 | EP-10 | Outsource Placement & Timesheet | PH2 | Task | Berita Acara (BA) Generation | Auto-generate BA PDF from approved timesheet: attendance table, total days | Critical | 8 | TSK-104 | BE+FE | Done
TSK-106 | EP-10 | Outsource Placement & Timesheet | PH2 | Task | Placement Contract Alert | H-30 alert: supervisor + Operation; H-7 escalation: GM/CLevel + Operation | High | 3 | TSK-100 | BE | Done
TSK-107 | EP-10 | Outsource Placement & Timesheet | PH2 | Task | Placement Renewal & Rate Amendment | Update end date; new rate with amandemen upload; history preserved | High | 5 | TSK-100 | BE+FE | Done
TSK-108 | EP-10 | Outsource Placement & Timesheet | PH2 | Task | Client KPI Assessment via Token | Operation sends token link to client PIC for outsource employee rating | High | 8 | TSK-100 | BE+FE | Done
TSK-109 | EP-10 | Outsource Placement & Timesheet | PH2 | Sub-task | Outsource Dashboard per Client | View all active placements per client; contract status; upcoming renewals | High | 5 | TSK-100 | FE | Done
TSK-110 | EP-10 | Outsource Placement & Timesheet | PH2 | Sub-task | SP for Outsource Employees | [DUPLICATE - see TSK-148] SP-O1/O2/O3 flow; triggered from client complaint logged by Sales | High | 5 | TSK-100 | BE+FE | DELETED - Duplicate of TSK-148
TSK-111 | EP-11 | Leave & Attendance | PH2 | Story | Leave Request System | Submit leave: type, dates, reason; balance check; 2-layer approval | Critical | 8 | TSK-026 | BE+FE | Done | M2.3 (CLAUDE.md TSK-019) — Leave request + 2-layer approval
TSK-112 | EP-11 | Leave & Attendance | PH2 | Task | Leave Balance Engine | Allocate annual leave per year; track balance; deduct on approval | Critical | 8 | TSK-111 | BE | Done | M2.3 — Leave balance engine (annual + sick + maternity)
TSK-113 | EP-11 | Leave & Attendance | PH2 | Task | Leave Types Configuration | Configure: Annual, Sick, Maternity, Bereavement, Marriage; each with rules | High | 5 | TSK-111 | BE+FE | Done | M2.3 — Leave types (ANNUAL/SICK/MATERNITY/...) config
TSK-114 | EP-11 | Leave & Attendance | PH2 | Task | Leave-Payroll Integration | Link approved leave to payroll deduction (unpaid/alpha days) | Critical | 5 | TSK-112 | BE | To Do
TSK-115 | EP-11 | Leave & Attendance | PH2 | Task | Leave During Extended Leave Logic | Skip assessment; put project assignment on hold during extended leave | High | 3 | TSK-112 | BE | To Do
TSK-116 | EP-11 | Leave & Attendance | PH2 | Sub-task | Leave Calendar View | Team calendar showing approved leaves; overlap detection | Medium | 5 | TSK-111 | FE | To Do
TSK-117 | EP-12 | Reimbursement | PH2 | Story | Reimbursement Request Flow | Submit: amount, currency, category, receipt upload; 2-layer approval | Critical | 8 | TSK-031 | BE+FE | Done | M2.3 (CLAUDE.md TSK-023) — Reimbursement request + 2-layer approval
TSK-118 | EP-12 | Reimbursement | PH2 | Task | Finance Reimbursement Processing | Finance verifies receipt; records transfer; posts to ledger; notifies employee | Critical | 5 | TSK-117 | BE+FE | Done | M2.3 — Finance reimbursement processing + transfer
TSK-119 | EP-12 | Reimbursement | PH2 | Task | Reimbursement History | Employee views all reimbursement history; status tracking | High | 3 | TSK-117 | FE | Done | M2.3 — Reimbursement history dengan filter
TSK-120 | EP-12 | Reimbursement | PH2 | Sub-task | Duplicate Reimbursement Detection | Warn on same date+amount+category combination | Medium | 2 | TSK-117 | BE | To Do
TSK-121 | EP-13 | Procurement & Asset Register | PH2 | Story | Procurement Request Flow | Submit: item, qty, est. price, reason; 2-layer approval; Finance confirms receipt | High | 8 | TSK-027 | BE+FE | Done | M2.3 — Procurement request + categories
TSK-122 | EP-13 | Procurement & Asset Register | PH2 | Task | Procurement Status Tracking | Status: Approved → In Process → Received; Finance confirms; notify requester | High | 5 | TSK-121 | BE+FE | Done | M2.3 — Procurement status tracking + PO + delivery
TSK-123 | EP-13 | Procurement & Asset Register | PH2 | Task | Asset Register | Register assets: name, value, location, purchase date; link from procurement | Medium | 5 | TSK-121 | BE+FE | To Do
TSK-124 | EP-13 | Procurement & Asset Register | PH2 | Sub-task | Procurement to Finance Integration | Auto-create expense transaction in Finance when procurement is completed | High | 3 | TSK-121 | BE | To Do
TSK-125 | EP-14 | Sales Leads & Funnel | PH3 | Story | Lead Management Module | CRUD leads: company, PIC, services, source, stage; assign + reassign | Critical | 13 | TSK-028 | BE+FE | Done | M3.1 (CLAUDE.md TSK-024) — Lead CRUD + assignee + estimated value
TSK-126 | EP-14 | Sales Leads & Funnel | PH3 | Task | Lead Funnel Stages | 6-stage funnel: Prospect/Qualified/Proposal/Negotiation/Closed Won/Lost | Critical | 5 | TSK-125 | BE+FE | Done | M3.1 — Lead 6-stage funnel (PROSPECT→...→CLOSED_WON/LOST)
TSK-127 | EP-14 | Sales Leads & Funnel | PH3 | Task | Lead Stage Transition Rules | Stage rules: PO required for Won; reason required for Lost; stage regression reason | High | 5 | TSK-126 | BE | Done | M3.1 — Stage transition rules + auto commission di CLOSED_WON
TSK-128 | EP-14 | Sales Leads & Funnel | PH3 | Task | Activity Log per Lead | Log: date, type (call/email/meeting), notes; history timeline view | High | 5 | TSK-125 | BE+FE | Done | M3.1 — LeadActivity log (call/email/meeting/note)
TSK-129 | EP-14 | Sales Leads & Funnel | PH3 | Task | Referral Tracking | Record referring employee; link to commission on Closed Won | High | 5 | TSK-125 | BE | To Do
TSK-130 | EP-14 | Sales Leads & Funnel | PH3 | Task | Direktur Closing Flow | Direktur marks Closed Won; no commission generated; tagged as Direktur-Driven | Critical | 5 | TSK-126 | BE+FE | To Do
TSK-131 | EP-14 | Sales Leads & Funnel | PH3 | Task | Lost Deal Re-engagement | Reopen Closed Lost lead; preserve full history; new stage tracking | Medium | 3 | TSK-126 | BE+FE | To Do
TSK-132 | EP-14 | Sales Leads & Funnel | PH3 | Sub-task | Lead Duplicate Detection | Warn on same company + service within 90 days | Medium | 2 | TSK-125 | BE | To Do
TSK-133 | EP-14 | Sales Leads & Funnel | PH3 | Sub-task | PO Upload & Finance Notification | Sales uploads PO on Closed Won; auto-notify Finance | Critical | 3 | TSK-126 | BE+FE | To Do
TSK-134 | EP-15 | Proposal Management | PH3 | Story | Proposal Creation & Versioning | Create proposal linked to lead; scope/timeline/pricing; version history | Critical | 8 | TSK-125 | BE+FE | To Do
TSK-135 | EP-15 | Proposal Management | PH3 | Task | Proposal Approval Flow | Manager → GM/CLevel approval; blocks "sent" without approval | Critical | 5 | TSK-134 | BE+FE | To Do
TSK-136 | EP-15 | Proposal Management | PH3 | Task | Proposal PDF Export | Generate PDF with all proposal fields; version stamp; send-date record | High | 5 | TSK-134 | BE+FE | To Do
TSK-137 | EP-15 | Proposal Management | PH3 | Task | Payment Terms (Termin) Setup | Define invoice terms per project: % + trigger (milestone/date); Finance notif | Critical | 8 | TSK-134 | BE+FE | To Do
TSK-138 | EP-15 | Proposal Management | PH3 | Sub-task | Proposal Status Tracking | Status: Draft/In Review/Approved/Sent/Won/Lost; with timestamps | High | 3 | TSK-134 | BE | To Do
TSK-139 | EP-16 | Sales Targets & Reports | PH3 | Story | Sales Target Setting | Manager sets individual targets; GM/CLevel sets dept target; monthly/quarterly | High | 8 | TSK-125 | BE+FE | To Do
TSK-140 | EP-16 | Sales Targets & Reports | PH3 | Task | Win Rate Calculation Engine | Win Rate = Closed Won / (Won + Lost); per salesperson; per service category | Critical | 5 | TSK-126 | BE | To Do
TSK-141 | EP-16 | Sales Targets & Reports | PH3 | Task | Sales Performance Report | Report: win rate, revenue, deal cycle, vs target; filter by period/salesperson | High | 8 | TSK-140 | BE+FE | To Do
TSK-142 | EP-16 | Sales Targets & Reports | PH3 | Task | Target vs Actual Tracking | Real-time progress bar per salesperson; mid-month <50% alert to manager | High | 5 | TSK-139 | BE+FE | To Do
TSK-143 | EP-16 | Sales Targets & Reports | PH3 | Sub-task | Direktur Deal Segmentation | Separate Direktur-Driven deals from team deals in all reports | High | 3 | TSK-130 | BE | To Do
TSK-144 | EP-17 | Warning Letter (SP) System | PH3 | Story | SP Manual Creation Flow | Operation creates SP manually; mandatory fields; GM/CLevel approval; digital ack | Critical | 8 | TSK-031 | BE+FE | To Do
TSK-145 | EP-17 | Warning Letter (SP) System | PH3 | Task | SP Sequence Enforcement | Enforce SP1→SP2→SP3 sequence; SP3 triggers layoff request to Direktur | Critical | 5 | TSK-144 | BE | To Do
TSK-146 | EP-17 | Warning Letter (SP) System | PH3 | Task | SP Employee Acknowledgment | SP shown in employee portal; digital acknowledgment required; 7-day escalation | Critical | 5 | TSK-144 | BE+FE | To Do
TSK-147 | EP-17 | Warning Letter (SP) System | PH3 | Task | SP History & Audit | Full SP history per employee; stored permanently; visible to Operation/GM | High | 3 | TSK-144 | BE+FE | To Do
TSK-148 | EP-17 | Warning Letter (SP) System | PH3 | Task | SP for Outsource (SP-O) Module | SP-O1/O2/O3 flow; Operation input after Sales reports client complaint | High | 5 | TSK-110 | BE+FE | Done
TSK-149 | EP-17 | Warning Letter (SP) System | PH3 | Sub-task | SP Layoff Request Trigger | SP3 creates layoff request; routes to Direktur for approval; no auto-fire | Critical | 3 | TSK-145 | BE | To Do
TSK-150 | EP-18 | Executive Portal | PH3 | Story | Executive Dashboard | Real-time KPI cards: People, Technology, Sales, Finance, Outsource | Critical | 13 | TSK-091 | BE+FE | Done
TSK-151 | EP-18 | Executive Portal | PH3 | Task | EBITDA Dashboard | EBITDA calculation; margin %; per revenue stream; 12-month trend chart | High | 8 | TSK-091 | BE+FE | Done
TSK-152 | EP-18 | Executive Portal | PH3 | Task | People Performance Overview | Bell curve distribution; dept avg; top/bottom performers; drill-down | High | 8 | TSK-080 | BE+FE | Done
TSK-153 | EP-18 | Executive Portal | PH3 | Task | Operational KPIs Dashboard | Hiring fill rate; onboarding completion; payroll timeliness; reimbursement TAT | High | 5 | TSK-029 | BE+FE | To Do
TSK-154 | EP-18 | Executive Portal | PH3 | Task | Executive Portal Access Gate | Direktur Utama only; redirect all others to Employee Portal | Critical | 2 | TSK-003 | BE | To Do
TSK-155 | EP-18 | Executive Portal | PH3 | Sub-task | Dashboard Drill-down Navigation | Click on metric → navigate to source module with filter applied | Medium | 5 | TSK-150 | FE | To Do
TSK-156 | EP-19 | Broadcast, Events & Company Info | PH3 | Story | Broadcast Module | Create broadcast: rich text, image, file attach; targeted audience; schedule | High | 8 | TSK-057 | BE+FE | To Do
TSK-157 | EP-19 | Broadcast, Events & Company Info | PH3 | Task | Audience Targeting Engine | Target by: global, department, level, or combination; permission by sender level | High | 5 | TSK-156 | BE | To Do
TSK-158 | EP-19 | Broadcast, Events & Company Info | PH3 | Task | Event Management Module | Create event: title, datetime, location, description, audience; RSVP | High | 5 | TSK-057 | BE+FE | To Do
TSK-159 | EP-19 | Broadcast, Events & Company Info | PH3 | Task | RSVP & Event Reminder | Employees RSVP Attending/Not; organizer sees list; H-1 reminder auto-sent | Medium | 5 | TSK-158 | BE+FE | To Do
TSK-160 | EP-19 | Broadcast, Events & Company Info | PH3 | Task | News Feed (Berita Perusahaan) | Chronological feed of broadcasts per employee; filter by dept/global | Medium | 5 | TSK-156 | FE | To Do
TSK-161 | EP-20 | Resignation & Offboarding | PH3 | Story | Resignation Submission Flow | Employee submits resign; 30-day notice validation; supervisor acknowledge | Critical | 5 | TSK-019 | BE+FE | To Do
TSK-162 | EP-20 | Resignation & Offboarding | PH3 | Task | Offboarding Checklist | Auto-create: asset return, handover, exit interview, clearance, final payroll | Critical | 5 | TSK-161 | BE+FE | To Do
TSK-163 | EP-20 | Resignation & Offboarding | PH3 | Task | Active Placement & PM Check on Resign | Block/warn if resigning employee has active outsource placement or is PM | Critical | 3 | TSK-161 | BE | To Do
TSK-164 | EP-20 | Resignation & Offboarding | PH3 | Task | Portal Access Revocation on Exit | Immediately revoke all access on last working day; invalidate sessions | Critical | 3 | TSK-019 | BE | To Do
TSK-165 | EP-20 | Resignation & Offboarding | PH3 | Task | Layoff Request & Approval Flow | Request layoff: 2-layer approval; offboarding same as resign; pesangon notes | Critical | 5 | TSK-031 | BE+FE | To Do
TSK-166 | EP-20 | Resignation & Offboarding | PH3 | Sub-task | Final Payroll Settlement | Trigger final prorated payroll on exit; link to Finance for processing | Critical | 3 | TSK-054 | BE | To Do
TSK-167 | EP-21 | AI Action Items & SP Drafting | PH4 | Story | AI Sales Action Item Generator | AI generates contextual action items per lead per stage; accept/edit/ignore | High | 13 | TSK-126 | BE+AI | To Do
TSK-168 | EP-21 | AI Action Items & SP Drafting | PH4 | Task | AI SP Draft Generator | AI drafts SP letter from rating history; editable before approval | High | 8 | TSK-081 | BE+AI | To Do
TSK-169 | EP-21 | AI Action Items & SP Drafting | PH4 | Task | AI Service Unavailability Fallback | Graceful degradation when AI unavailable; show manual input option | Medium | 3 | TSK-167 | BE+FE | To Do
TSK-170 | EP-21 | AI Action Items & SP Drafting | PH4 | Sub-task | Action Item Tracking | Track accepted/edited/ignored action items; completion rate per sales | Medium | 5 | TSK-167 | BE+FE | To Do
TSK-171 | EP-22 | Digital Signature (BA & SP) | PH4 | Story | BA Digital Signature (Client Token) | Send unique token link to client PIC; signature UI; both parties sign; PDF final | Critical | 13 | TSK-105 | BE+FE | To Do
TSK-172 | EP-22 | Digital Signature (BA & SP) | PH4 | Task | Token Generation & Expiry | Unique token per BA per period; expiry handling; regenerate flow | Critical | 5 | TSK-171 | BE | To Do
TSK-173 | EP-22 | Digital Signature (BA & SP) | PH4 | Task | Client Signature Interface | No-login page via token; display BA detail; draw/type signature; confirm | Critical | 8 | TSK-171 | FE | To Do
TSK-174 | EP-22 | Digital Signature (BA & SP) | PH4 | Task | Client KPI Form via Token | Same token mechanism for client to rate outsource employee performance | High | 5 | TSK-108 | FE | To Do
TSK-175 | EP-22 | Digital Signature (BA & SP) | PH4 | Sub-task | Signed PDF Generation | Embed both digital signatures into BA PDF; store final version in system | Critical | 5 | TSK-173 | BE | To Do
TSK-176 | EP-23 | AI Executive Summary | PH4 | Story | Monthly AI Executive Summary | Auto-generate narrative + chart summary at month start for previous month | High | 13 | TSK-150 | BE+AI | To Do
TSK-177 | EP-23 | AI Executive Summary | PH4 | Task | Data Aggregation for Summary | Pull all KPIs from all modules; structure for AI prompt engineering | High | 8 | TSK-176 | BE | To Do
TSK-178 | EP-23 | AI Executive Summary | PH4 | Task | AI Narrative Generation | Send aggregated data to AI; generate: achievements, risks, recommendations | High | 8 | TSK-177 | BE+AI | To Do
TSK-179 | EP-23 | AI Executive Summary | PH4 | Task | Executive Summary PDF Export | Export summary with charts as downloadable PDF; shareable link | High | 5 | TSK-176 | BE+FE | To Do
TSK-180 | EP-23 | AI Executive Summary | PH4 | Sub-task | On-demand Dept Summary | GM/CLevel can request AI summary for their department anytime | Medium | 5 | TSK-178 | BE+FE | To Do
TSK-181 | EP-24 | Data Migration & Import Tools | PH4 | Story | Bulk Import via Excel Template | Import employees, clients, org structure via Excel template; validation + error report | Critical | 13 | TSK-013 | BE+FE | To Do
TSK-182 | EP-24 | Data Migration & Import Tools | PH4 | Task | Import Validation Engine | Validate: required fields, duplicate NIK, dept existence, salary range | Critical | 8 | TSK-181 | BE | To Do
TSK-183 | EP-24 | Data Migration & Import Tools | PH4 | Task | Payroll History Import | Import historical pay slips per employee since joining; PDF generation | High | 8 | TSK-051 | BE | To Do
TSK-184 | EP-24 | Data Migration & Import Tools | PH4 | Task | Jira Project Import | Parse Jira export; map projects/epics/issues to IDEA project structure | High | 8 | TSK-073 | BE | To Do
TSK-185 | EP-24 | Data Migration & Import Tools | PH4 | Task | Rollback & Recovery Plan | Pre-cutover backup; rollback trigger; restore to pre-migration state | Critical | 8 | TSK-181 | BE+DevOps | To Do
TSK-186 | EP-24 | Data Migration & Import Tools | PH4 | Sub-task | Migration Progress Dashboard | Real-time import progress; error log; admin download error report | High | 5 | TSK-181 | FE | To Do
TSK-187 | EP-25 | Reporting & Analytics | PH4 | Story | Comprehensive Report Module | All reports: Finance, HR, Sales, Operations; filters; export PDF+Excel | High | 13 | TSK-098 | BE+FE | To Do
TSK-188 | EP-25 | Reporting & Analytics | PH4 | Task | HR Analytics Dashboard | Headcount trend; turnover rate; hire vs resign; dept distribution; tenure | High | 8 | TSK-013 | BE+FE | To Do
TSK-189 | EP-25 | Reporting & Analytics | PH4 | Task | Sales Analytics Dashboard | Pipeline value; conversion by stage; revenue forecast; team comparison | High | 8 | TSK-140 | BE+FE | To Do
TSK-190 | EP-25 | Reporting & Analytics | PH4 | Task | Finance KPI Widgets for Executive | Outstanding receivables; burn rate; EBITDA trend; cash runway estimate | High | 8 | TSK-150 | BE+FE | To Do
TSK-191 | EP-25 | Reporting & Analytics | PH4 | Task | System Audit Log Report | Admin views all critical action logs; filter by user/date/action type; export | High | 5 | TSK-011 | BE+FE | To Do
TSK-192 | EP-25 | Reporting & Analytics | PH4 | Sub-task | Scheduled Report Generation | Auto-generate and notify key reports at configured intervals (monthly/weekly) | Medium | 5 | TSK-187 | BE | To Do
TSK-193 | EP-01 | Authentication & Authorization | PH1 | Task | Wakil Direktur Utama Role in RBAC | Add 'Wakil Direktur Utama' as separate role with identical permission set to Direktur Utama; ensure audit log records persona name explicitly per US-EX-005 | Critical | 5 | TSK-003 | BE | Done
TSK-194 | EP-05 | Payroll Processing | PH1 | Story | Auto-Create Variable Payroll Line on Closed Won | When sales deal Closed Won (by Sales PIC, not Direktur), auto-create draft variable component line in current payroll period with commission % calculation | High | 8 | TSK-046, TSK-126 | BE+FE | Done
TSK-195 | EP-14 | Sales Leads & Funnel | PH3 | Task | AI Sales Action Item Module (US-SM-005) | User-facing module for AI-generated action items per lead per stage; Accept/Edit/Ignore controls; widget in Sales dashboard. Links to TSK-167 (AI engine). | Medium | 8 | TSK-167 | FE | To Do
TSK-196 | EP-10 | Outsource Placement & Timesheet | PH2 | Story | Client Complaint Logging Module | Sales PIC logs client complaints linked to outsource employee; auto-notify Operation; complaint detail + severity + status tracking. Feeds SP-O flow. | High | 5 | TSK-028, TSK-100 | BE+FE | To Do
TSK-197 | EP-02 | Employee & Organization Master Data | PH1 | Story | Promotion UI Page (US-OP-012) | Operation-facing UI for promotion: select employee, new level, salary suggestion, approval routing display, effective date. Backend in TSK-022. | High | 5 | TSK-022 | FE | Done
TSK-198 | EP-02 | Employee & Organization Master Data | PH1 | Story | Mutation UI Page (US-OP-013) | Operation-facing UI for inter-dept mutation: select employee, target dept, active project resolution check, dual GM approval status. Backend in TSK-021. | Medium | 5 | TSK-021 | FE | Done
TSK-199 | EP-02 | Employee & Organization Master Data | PH1 | Story | PKWT Renewal Decision UI (US-OP-014) | Operation UI for expiring contract decisions: Renew/End/Convert. Shows H-30 + H-7 alerts as actionable list. Dashboard widget for next-60-days expirations. | Critical | 5 | TSK-020, TSK-059 | FE | Done
TSK-200 | EP-09 | Finance & Accounting | PH2 | Task | Invoice Termin UI on Project Management | Add 'Termin & Invoice' panel to Project Management mockup/page: define %, trigger (milestone/date), Finance notification status. Realizes TSK-137 in UI. | High | 5 | TSK-137 | FE | To Do
TSK-201 | EP-18 | Executive Portal | PH3 | Task | Wakil Direktur Audit Persona Display | Executive Portal displays current user persona (Direktur Utama / Wakil Direktur Utama) in header; all audit-logged actions show explicit persona attribution in reports/dashboards. | High | 3 | TSK-193 | FE | Done
TSK-022B | EP-07 | Project Management | PH2 | Refactor | PM hierarchy Phase>Epic>Task>Subtask + comments | Replace Milestone with Phase (4-level), add Epic & Subtask, slug Jira-style + story_points, markdown comments via kanban card | Critical | 17 | TSK-022C | Backend+Frontend | Done | M2.1 (refactor) — commit e562724
TSK-022C | EP-07+EP-09 | Project Management → Finance | PH2 | Refactor | Extract Invoice from Project to Finance domain | Pindahkan tabel project_invoices ke app/finance/Invoice; trigger source milestone → Phase completion | Critical | 10 | TSK-022 | Backend+Frontend | Done | M2.2 (refactor) — commit 77dbc16
TSK-022D | EP-09 | Finance Invoice UI | PH2 | Feature | Finance Invoice UI — list, create, payment, aging | InvoicesTab di FinancePage dengan KPI strip, status filter, aging bucket color, payment tracking modal, PPN auto-compute | High | 10 | TSK-022C | Frontend | Done | M2.2 — commit af20538

## 🔵 PH1
PHASE 1 — FOUNDATION
Auth, Core Data, Operation (Hiring + Payroll + Onboarding)
Task ID | Epic ID | Epic Name | Phase | Type | Title | Description | Priority | Story Pts | Dependencies | Role | Status
EP-01 ▸ Authentication & Authorization [12 tasks ¦ 71 story pts]
TSK-001 | EP-01 | Authentication & Authorization | PH1 | Story | Single Login Portal Setup | Create unified login page at portal.ide.asia with company branding | Critical | 8 |  | BE+FE | To Do
TSK-002 | EP-01 | Authentication & Authorization | PH1 | Task | JWT Authentication Implementation | Implement JWT token-based auth with refresh token mechanism | Critical | 5 | TSK-001 | BE | To Do
TSK-003 | EP-01 | Authentication & Authorization | PH1 | Task | Role-Based Access Control (RBAC) Engine | Build RBAC middleware; map Level 1-6 to permission sets | Critical | 8 | TSK-002 | BE | To Do
TSK-004 | EP-01 | Authentication & Authorization | PH1 | Task | Permission Matrix Implementation | Implement all 12 permission matrix rules per module per role | Critical | 13 | TSK-003 | BE | To Do
TSK-005 | EP-01 | Authentication & Authorization | PH1 | Task | Session Management & Auto-logout | Session timeout, concurrent session control, auto-save drafts on timeout | High | 5 | TSK-002 | BE | To Do
TSK-006 | EP-01 | Authentication & Authorization | PH1 | Task | Account Lock After Failed Attempts | Lock account after 5 failed logins; 30-min timeout; admin unlock | High | 3 | TSK-002 | BE | To Do
TSK-007 | EP-01 | Authentication & Authorization | PH1 | Task | Password Reset Flow | Forgot password flow via email OTP | Medium | 3 | TSK-001 | BE+FE | To Do
TSK-008 | EP-01 | Authentication & Authorization | PH1 | Task | Dark Mode & Accessibility Settings | Toggle dark/light mode; font size control; contrast settings | Medium | 5 | TSK-001 | FE | To Do
TSK-009 | EP-01 | Authentication & Authorization | PH1 | Task | Mobile Responsive Layout Framework | Setup responsive grid; breakpoints for mobile/tablet/desktop | Critical | 8 | TSK-001 | FE | To Do
TSK-010 | EP-01 | Authentication & Authorization | PH1 | Sub-task | Login Page UI | Design and build login page with company logo, responsive layout | High | 3 | TSK-001 | FE | To Do
TSK-011 | EP-01 | Authentication & Authorization | PH1 | Sub-task | Audit Trail Logger | Log all critical actions: who, what, when, IP address | High | 5 | TSK-003 | BE | To Do
TSK-012 | EP-01 | Authentication & Authorization | PH1 | Sub-task | Global Search (Employee & Project) | Search bar in header; search employees and projects across system | Medium | 5 | TSK-004 | BE+FE | To Do
EP-02 ▸ Employee & Organization Master Data [16 tasks ¦ 86 story pts]
TSK-013 | EP-02 | Employee & Organization Master Data | PH1 | Story | Employee Master Data Module | CRUD for all employee data including PKWT/PKWTT, Type A/B/C | Critical | 13 | TSK-003 | BE+FE | To Do
TSK-014 | EP-02 | Employee & Organization Master Data | PH1 | Task | Employee Profile Form | All fields: identity, contact, bank, BPJS, employment details | Critical | 8 | TSK-013 | FE | To Do
TSK-015 | EP-02 | Employee & Organization Master Data | PH1 | Task | Organization Hierarchy Tree | Tree data structure for parent-child reporting; circular reference validation | Critical | 8 | TSK-013 | BE | To Do
TSK-016 | EP-02 | Employee & Organization Master Data | PH1 | Task | Department & Level Management | CRUD for departments; level 1-6 configuration per dept | Critical | 5 | TSK-013 | BE+FE | To Do
TSK-017 | EP-02 | Employee & Organization Master Data | PH1 | Task | Salary Range Configuration per Level | Set min/max salary range per level; used for promotion suggestion | High | 3 | TSK-016 | BE+FE | To Do
TSK-018 | EP-02 | Employee & Organization Master Data | PH1 | Task | BPJS Configuration per Employee | Configure BPJS Kesehatan & Ketenagakerjaan split per employee/level | Critical | 5 | TSK-013 | BE+FE | To Do
TSK-019 | EP-02 | Employee & Organization Master Data | PH1 | Task | Employee Status Management | Status: Active, Probation, On Leave, Terminated, Resigned; auto-access revoke | Critical | 5 | TSK-013 | BE | To Do
TSK-020 | EP-02 | Employee & Organization Master Data | PH1 | Task | PKWT Contract Tracking | Store contract start/end date; alert H-30 and H-7 to supervisor + Operation | High | 5 | TSK-013 | BE | To Do
TSK-021 | EP-02 | Employee & Organization Master Data | PH1 | Task | Mutation (Department Transfer) Flow | Transfer employee between depts; preserve history; notify PM if in project | High | 5 | TSK-015 | BE+FE | To Do
TSK-022 | EP-02 | Employee & Organization Master Data | PH1 | Task | Promotion Flow | Change level; suggest salary range; set effective date; audit trail | High | 5 | TSK-017 | BE+FE | To Do
TSK-023 | EP-02 | Employee & Organization Master Data | PH1 | Task | Employee Reactivation | Re-activate former employee; restore all history; re-onboard flow | Medium | 3 | TSK-019 | BE+FE | To Do
TSK-024 | EP-02 | Employee & Organization Master Data | PH1 | Task | Org Chart Auto-generation | Visual org chart from hierarchy data; tree + list view; all employees | High | 8 | TSK-015 | FE | To Do
TSK-025 | EP-02 | Employee & Organization Master Data | PH1 | Sub-task | Employee List & Filter View | Filterable employee list: by dept, level, status, type | High | 3 | TSK-013 | FE | To Do
TSK-026 | EP-02 | Employee & Organization Master Data | PH1 | Sub-task | Work Calendar Management | Set working days, holidays, dept override; affects payroll & leave | Critical | 5 | TSK-016 | BE+FE | To Do
TSK-027 | EP-02 | Employee & Organization Master Data | PH1 | Sub-task | Vendor List Management | CRUD vendor: name, contact, category; used in procurement | Medium | 2 | TSK-013 | BE+FE | To Do
TSK-028 | EP-02 | Employee & Organization Master Data | PH1 | Sub-task | Client Master Data | CRUD client: company, PIC, contract details; linked to outsource & project | Critical | 3 | TSK-013 | BE+FE | To Do
EP-03 ▸ Hiring & Recruitment [10 tasks ¦ 57 story pts]
TSK-029 | EP-03 | Hiring & Recruitment | PH1 | Story | Hiring Request Workflow | End-to-end hiring request: submit → 2-layer approval → Operation receives | Critical | 8 | TSK-004 | BE+FE | To Do
TSK-030 | EP-03 | Hiring & Recruitment | PH1 | Task | Hiring Request Form | Fields: position, level, dept, reason (new/replacement), target date, description | Critical | 5 | TSK-029 | FE | To Do
TSK-031 | EP-03 | Hiring & Recruitment | PH1 | Task | 2-Layer Approval Engine (Generic) | Reusable approval component: Layer1 (supervisor) → Layer2 (GM/CLevel) | Critical | 8 | TSK-003 | BE | To Do
TSK-032 | EP-03 | Hiring & Recruitment | PH1 | Task | Candidate Management | Add candidates: name, contact, CV upload, source; link to hiring request | Critical | 8 | TSK-029 | BE+FE | To Do
TSK-033 | EP-03 | Hiring & Recruitment | PH1 | Task | Selection Stage Configuration | Configure stages per position; record Pass/Fail + notes per stage | High | 5 | TSK-032 | BE+FE | To Do
TSK-034 | EP-03 | Hiring & Recruitment | PH1 | Task | Offering Letter Generation | Generate offering letter PDF; fields: position, salary, start date; approval required | Critical | 8 | TSK-033 | BE+FE | To Do
TSK-035 | EP-03 | Hiring & Recruitment | PH1 | Task | Candidate Status Tracking | Track: Screening → Interview → Offering → Hired / Rejected | High | 5 | TSK-032 | BE+FE | To Do
TSK-036 | EP-03 | Hiring & Recruitment | PH1 | Task | Internal Job Board | Display approved job openings; visible to all employees | Medium | 3 | TSK-029 | FE | To Do
TSK-037 | EP-03 | Hiring & Recruitment | PH1 | Sub-task | Duplicate Request Detection | Warn if similar position already requested in same month | Medium | 2 | TSK-029 | BE | To Do
TSK-038 | EP-03 | Hiring & Recruitment | PH1 | Sub-task | Hiring Dashboard for Operation | View all open requests, pipeline status, fill rate metrics | High | 5 | TSK-029 | FE | To Do
EP-04 ▸ Onboarding Management [7 tasks ¦ 37 story pts]
TSK-039 | EP-04 | Onboarding Management | PH1 | Story | Automated Onboarding Checklist | Auto-create checklist when candidate status = Hired; track completion | Critical | 8 | TSK-035 | BE+FE | To Do
TSK-040 | EP-04 | Onboarding Management | PH1 | Task | Welcome Page for New Employees | Show welcome banner with text, images, handbook links on first login | High | 5 | TSK-039 | FE | To Do
TSK-041 | EP-04 | Onboarding Management | PH1 | Task | Onboarding Checklist Items | Configurable checklist: contract signing, data entry, asset receipt, orientation | High | 5 | TSK-039 | BE+FE | To Do
TSK-042 | EP-04 | Onboarding Management | PH1 | Task | H-3 Pre-join Preparation Alert | Auto-alert Operation H-3 before join date to prepare accounts and assets | High | 3 | TSK-039 | BE | To Do
TSK-043 | EP-04 | Onboarding Management | PH1 | Task | Account Activation on Join Date | Auto-activate employee account on join date; send login credentials | Critical | 3 | TSK-039 | BE | To Do
TSK-044 | EP-04 | Onboarding Management | PH1 | Task | Probation Assessment Flow | Separate assessment form for Month 1, 2, 3 of probation; extend/pass/fail | High | 8 | TSK-039 | BE+FE | To Do
TSK-045 | EP-04 | Onboarding Management | PH1 | Sub-task | Company Info Portal (CMS) | Operation manages: visi/misi, policies, SOP, handbook, templates; searchable | High | 5 | TSK-039 | BE+FE | To Do
EP-05 ▸ Payroll Processing [11 tasks ¦ 62 story pts]
TSK-046 | EP-05 | Payroll Processing | PH1 | Story | Payroll Component Configuration | Setup fixed & variable salary components; BPJS; custom deductions per employee | Critical | 8 | TSK-018 | BE+FE | To Do
TSK-047 | EP-05 | Payroll Processing | PH1 | Task | Monthly Attendance Input by Operation | Operation inputs total working days + overtime per employee before cutoff | Critical | 5 | TSK-046 | BE+FE | To Do
TSK-048 | EP-05 | Payroll Processing | PH1 | Task | Payroll Calculation Engine | Calculate: gross = fixed + variable + OT; net = gross - BPJS - PPh21 - deductions | Critical | 13 | TSK-046 | BE | To Do
TSK-049 | EP-05 | Payroll Processing | PH1 | Task | PPh 21 Manual Input per Employee | Finance inputs PPh21 amount per employee; stored as deduction component | Critical | 5 | TSK-048 | BE+FE | To Do
TSK-050 | EP-05 | Payroll Processing | PH1 | Task | Payroll Review & Approval by GM/CLevel | Payroll summary review screen; approval required before processing | Critical | 5 | TSK-048 | BE+FE | To Do
TSK-051 | EP-05 | Payroll Processing | PH1 | Task | Pay Slip Generation (PDF) | Generate individual pay slip PDF; all components itemized; publish to portal | Critical | 8 | TSK-050 | BE+FE | To Do
TSK-052 | EP-05 | Payroll Processing | PH1 | Task | Pay Slip History Access | Employee views all pay slips since joining; download as PDF | Critical | 3 | TSK-051 | FE | To Do
TSK-053 | EP-05 | Payroll Processing | PH1 | Task | THR Processing Module | Configure THR components; calculate prorated for <1yr; separate payment flow | High | 5 | TSK-048 | BE+FE | To Do
TSK-054 | EP-05 | Payroll Processing | PH1 | Task | Prorated Final Payroll (Exit) | Calculate prorated salary on exit based on effective working days | Critical | 5 | TSK-048 | BE | To Do
TSK-055 | EP-05 | Payroll Processing | PH1 | Sub-task | Payroll Period Configuration | Set payroll cutoff and disbursement dates; configurable per period | High | 3 | TSK-046 | BE+FE | To Do
TSK-056 | EP-05 | Payroll Processing | PH1 | Sub-task | Payroll Duplicate Prevention | Block second submission for same employee in same period | Critical | 2 | TSK-047 | BE | To Do
EP-06 ▸ Notification Engine [5 tasks ¦ 29 story pts]
TSK-057 | EP-06 | Notification Engine | PH1 | Story | In-App Notification System | Real-time in-app notifications; notification bell; read/unread state | Critical | 8 | TSK-001 | BE+FE | To Do
TSK-058 | EP-06 | Notification Engine | PH1 | Task | Notification Templates | Template per event: approval request, alert, deadline, system message | High | 5 | TSK-057 | BE | To Do
TSK-059 | EP-06 | Notification Engine | PH1 | Task | Alert Rules Engine | Configure: PKWT H-30/H-7, contract renewal H-30/H-7, task H-3/H-1, payroll | High | 8 | TSK-057 | BE | To Do
TSK-060 | EP-06 | Notification Engine | PH1 | Task | Approval Chain Notifications | Notify correct approver at each layer; escalate if approver inactive | Critical | 5 | TSK-031 | BE | To Do
TSK-061 | EP-06 | Notification Engine | PH1 | Sub-task | Notification Retry & Failure Handling | Retry failed notifications; log failures; escalate to admin after 3 retries | Medium | 3 | TSK-057 | BE | To Do

## 🟣 PH2
PHASE 2 — CORE OPERATIONS
Technology Dept, Finance Dept, Global Self-Service, Outsource
Task ID | Epic ID | Epic Name | Phase | Type | Title | Description | Priority | Story Pts | Dependencies | Role | Status
EP-07 ▸ Project Management [15 tasks ¦ 102 story pts]
TSK-062 | EP-07 | Project Management | PH2 | Story | Project CRUD & Configuration | Create/edit projects: Client, Internal, R&D types; link to Sales deal or Direktur | Critical | 8 | TSK-028 | BE+FE | To Do
TSK-063 | EP-07 | Project Management | PH2 | Task | Project Team Assignment | Assign PM + members; set role & allocation %; over-allocation warning | High | 5 | TSK-062 | BE+FE | To Do
TSK-064 | EP-07 | Project Management | PH2 | Task | Kanban Board | Columns: Backlog/In Progress/Review/Done; drag-drop; task detail modal | Critical | 13 | TSK-062 | FE | To Do
TSK-065 | EP-07 | Project Management | PH2 | Task | Gantt Chart View | Timeline view of milestones & tasks; dependency lines; progress % | High | 13 | TSK-062 | FE | To Do
TSK-066 | EP-07 | Project Management | PH2 | Task | Task Management | CRUD tasks: title, description, assignee, deadline, priority, milestone link | Critical | 8 | TSK-064 | BE+FE | To Do
TSK-067 | EP-07 | Project Management | PH2 | Task | Milestone Management | CRUD milestones; auto-calculate progress from tasks; block completion if open tasks | High | 5 | TSK-066 | BE+FE | To Do
TSK-068 | EP-07 | Project Management | PH2 | Task | Technical Documentation Module | Folder structure; file upload with versioning; project-member-only access | High | 8 | TSK-062 | BE+FE | To Do
TSK-069 | EP-07 | Project Management | PH2 | Task | Project Closing Flow | Closing report form; client sign-off upload; approval; Finance + Sales notif | High | 8 | TSK-067 | BE+FE | To Do
TSK-070 | EP-07 | Project Management | PH2 | Task | Change Request (CR) Module | CR form: scope/timeline/cost impact; approval; trigger Sales + Finance update | High | 5 | TSK-062 | BE+FE | To Do
TSK-071 | EP-07 | Project Management | PH2 | Task | Internal Project Approval (Direktur) | Internal project requires Direktur approval; man-hour tracking; no billing | High | 5 | TSK-062 | BE+FE | To Do
TSK-072 | EP-07 | Project Management | PH2 | Task | Sub-contractor in Project | Add external sub-contractor as project member; link cost to Finance | Medium | 5 | TSK-063 | BE+FE | To Do
TSK-073 | EP-07 | Project Management | PH2 | Task | Jira Import Tool | Import existing projects from Jira JSON/CSV; map to system entities | High | 8 | TSK-062 | BE | To Do
TSK-074 | EP-07 | Project Management | PH2 | Sub-task | Project Status Management | Status flow: Draft/Active/On Hold/Completed/Terminated; Direktur override | Critical | 3 | TSK-062 | BE | To Do
TSK-075 | EP-07 | Project Management | PH2 | Sub-task | Task Deadline Notifications | H-3 and H-1 alerts to assignee and PM; overdue flag | High | 3 | TSK-066 | BE | To Do
TSK-076 | EP-07 | Project Management | PH2 | Sub-task | Project Report per Employee | Summary: projects, contribution, history; export PDF; access by level | High | 5 | TSK-062 | BE+FE | To Do
EP-08 ▸ Employee Assessment & OKR [10 tasks ¦ 55 story pts]
TSK-077 | EP-08 | Employee Assessment & OKR | PH2 | Story | OKR Framework Setup | Quarterly OKR: supervisor sets Objectives + Key Results; bulanan evaluasi | Critical | 8 | TSK-016 | BE+FE | To Do
TSK-078 | EP-08 | Employee Assessment & OKR | PH2 | Task | Monthly Assessment Form | Input OKR progress % + weighted scores; auto-calculate final score | Critical | 8 | TSK-077 | BE+FE | To Do
TSK-079 | EP-08 | Employee Assessment & OKR | PH2 | Task | Assessment Weight Configuration | GM/CLevel configure OKR weight vs Weighted Score weight per dept | High | 3 | TSK-078 | BE+FE | To Do
TSK-080 | EP-08 | Employee Assessment & OKR | PH2 | Task | Performance Score Calculation Engine | Final Score = (OKR × weight%) + (Weighted × weight%); threshold logic | Critical | 8 | TSK-078 | BE | To Do
TSK-081 | EP-08 | Employee Assessment & OKR | PH2 | Task | SP Threshold Flag System | Month 1 <60: yellow; Month 2: orange; Month 3: auto-trigger SP to Operation | Critical | 5 | TSK-080 | BE | To Do
TSK-082 | EP-08 | Employee Assessment & OKR | PH2 | Task | Rating History View | Employee views all ratings since joining; trend graph; per-dept history preserved | High | 5 | TSK-078 | FE | To Do
TSK-083 | EP-08 | Employee Assessment & OKR | PH2 | Task | Sales OKR Auto-pull | Auto-populate win rate & revenue actual from Sales module into OKR | High | 5 | TSK-077 | BE | To Do
TSK-084 | EP-08 | Employee Assessment & OKR | PH2 | Task | 360-Degree Feedback Module | Optional per dept; peers input feedback; separate from official rating | Medium | 8 | TSK-078 | BE+FE | To Do
TSK-085 | EP-08 | Employee Assessment & OKR | PH2 | Sub-task | Late Assessment Flagging | Flag late submissions; notify GM/CLevel; still accepted with flag | Medium | 2 | TSK-078 | BE | To Do
TSK-086 | EP-08 | Employee Assessment & OKR | PH2 | Sub-task | Assessment Leave Skip Logic | Skip assessment months for employees on extended approved leave | Critical | 3 | TSK-081 | BE | To Do
EP-09 ▸ Finance & Accounting [13 tasks ¦ 82 story pts]
TSK-087 | EP-09 | Finance & Accounting | PH2 | Story | Chart of Accounts (CoA) Module | Import existing CoA; CRUD; mandatory mapping for all transactions | Critical | 8 | TSK-028 | BE+FE | To Do
TSK-088 | EP-09 | Finance & Accounting | PH2 | Task | Daily Transaction Input | Accrual basis; multi-currency; CoA mapping; attach document; status flow | Critical | 8 | TSK-087 | BE+FE | To Do
TSK-089 | EP-09 | Finance & Accounting | PH2 | Task | Multi-Currency Engine | Store original currency + exchange rate + IDR equivalent; IDR as functional | Critical | 8 | TSK-088 | BE | To Do
TSK-090 | EP-09 | Finance & Accounting | PH2 | Task | Transaction Reversal | Create reversal entry for posted transactions; cannot edit posted | Critical | 5 | TSK-088 | BE+FE | To Do
TSK-091 | EP-09 | Finance & Accounting | PH2 | Task | P&L Report Generation | Filter by period; breakdown by dept & revenue stream; comparison MoM/YoY | Critical | 8 | TSK-087 | BE+FE | To Do
TSK-092 | EP-09 | Finance & Accounting | PH2 | Task | Balance Sheet Generation | As-of-date snapshot; auto-validate assets = liabilities + equity | High | 8 | TSK-087 | BE+FE | To Do
TSK-093 | EP-09 | Finance & Accounting | PH2 | Task | Cash Flow Statement | Operating/Investing/Financing cash flow; period filter | High | 8 | TSK-087 | BE+FE | To Do
TSK-094 | EP-09 | Finance & Accounting | PH2 | Task | PPh 21 Monthly Recap | Auto-aggregate PPh21 inputs from payroll; export for manual reporting | High | 5 | TSK-049 | BE+FE | To Do
TSK-095 | EP-09 | Finance & Accounting | PH2 | Task | PPN Recap Module | Tag transactions as PPN-applicable; monthly recap; export for manual SPT | High | 5 | TSK-088 | BE+FE | To Do
TSK-096 | EP-09 | Finance & Accounting | PH2 | Task | Invoice Tracking | Manual invoice number input; link to project/outsource; status tracking; alerts | Critical | 8 | TSK-088 | BE+FE | To Do
TSK-097 | EP-09 | Finance & Accounting | PH2 | Task | Invoice Overdue Alerts | Auto-alert at H+7, H+14, H+30 from due date; show in Executive dashboard | High | 3 | TSK-096 | BE | To Do
TSK-098 | EP-09 | Finance & Accounting | PH2 | Task | Report Export (PDF + Excel) | Export all financial reports as PDF and Excel; chart included in PDF | High | 5 | TSK-091 | BE+FE | To Do
TSK-099 | EP-09 | Finance & Accounting | PH2 | Sub-task | Duplicate Transaction Detection | Warn on same amount+date+CoA+description combination | High | 3 | TSK-088 | BE | To Do
EP-10 ▸ Outsource Placement & Timesheet [11 tasks ¦ 65 story pts]
TSK-100 | EP-10 | Outsource Placement & Timesheet | PH2 | Story | Outsource Placement Management | CRUD placement: employee, client, position, dates, rate, billing type | Critical | 8 | TSK-028 | BE+FE | To Do
TSK-101 | EP-10 | Outsource Placement & Timesheet | PH2 | Task | Multi-Client Placement Support | One employee → multiple simultaneous placements; allocation split | High | 5 | TSK-100 | BE+FE | To Do
TSK-102 | EP-10 | Outsource Placement & Timesheet | PH2 | Task | Billing Configuration per Client | Toggle: flat monthly OR per-timesheet; rate input; amandemen support | Critical | 5 | TSK-100 | BE+FE | To Do
TSK-103 | EP-10 | Outsource Placement & Timesheet | PH2 | Task | Monthly Timesheet Submission | Employee submits timesheet: daily attendance, absence, overtime per client | Critical | 8 | TSK-100 | BE+FE | To Do
TSK-104 | EP-10 | Outsource Placement & Timesheet | PH2 | Task | Timesheet Approval by Operation | Operation review/approve/reject timesheet; rejection returns to employee | Critical | 5 | TSK-103 | BE+FE | To Do
TSK-105 | EP-10 | Outsource Placement & Timesheet | PH2 | Task | Berita Acara (BA) Generation | Auto-generate BA PDF from approved timesheet: attendance table, total days | Critical | 8 | TSK-104 | BE+FE | To Do
TSK-106 | EP-10 | Outsource Placement & Timesheet | PH2 | Task | Placement Contract Alert | H-30 alert: supervisor + Operation; H-7 escalation: GM/CLevel + Operation | High | 3 | TSK-100 | BE | To Do
TSK-107 | EP-10 | Outsource Placement & Timesheet | PH2 | Task | Placement Renewal & Rate Amendment | Update end date; new rate with amandemen upload; history preserved | High | 5 | TSK-100 | BE+FE | To Do
TSK-108 | EP-10 | Outsource Placement & Timesheet | PH2 | Task | Client KPI Assessment via Token | Operation sends token link to client PIC for outsource employee rating | High | 8 | TSK-100 | BE+FE | To Do
TSK-109 | EP-10 | Outsource Placement & Timesheet | PH2 | Sub-task | Outsource Dashboard per Client | View all active placements per client; contract status; upcoming renewals | High | 5 | TSK-100 | FE | To Do
TSK-110 | EP-10 | Outsource Placement & Timesheet | PH2 | Sub-task | SP for Outsource Employees | SP-O1/O2/O3 flow; triggered from client complaint logged by Sales | High | 5 | TSK-100 | BE+FE | To Do
EP-11 ▸ Leave & Attendance [6 tasks ¦ 34 story pts]
TSK-111 | EP-11 | Leave & Attendance | PH2 | Story | Leave Request System | Submit leave: type, dates, reason; balance check; 2-layer approval | Critical | 8 | TSK-026 | BE+FE | To Do
TSK-112 | EP-11 | Leave & Attendance | PH2 | Task | Leave Balance Engine | Allocate annual leave per year; track balance; deduct on approval | Critical | 8 | TSK-111 | BE | To Do
TSK-113 | EP-11 | Leave & Attendance | PH2 | Task | Leave Types Configuration | Configure: Annual, Sick, Maternity, Bereavement, Marriage; each with rules | High | 5 | TSK-111 | BE+FE | To Do
TSK-114 | EP-11 | Leave & Attendance | PH2 | Task | Leave-Payroll Integration | Link approved leave to payroll deduction (unpaid/alpha days) | Critical | 5 | TSK-112 | BE | To Do
TSK-115 | EP-11 | Leave & Attendance | PH2 | Task | Leave During Extended Leave Logic | Skip assessment; put project assignment on hold during extended leave | High | 3 | TSK-112 | BE | To Do
TSK-116 | EP-11 | Leave & Attendance | PH2 | Sub-task | Leave Calendar View | Team calendar showing approved leaves; overlap detection | Medium | 5 | TSK-111 | FE | To Do
EP-12 ▸ Reimbursement [4 tasks ¦ 18 story pts]
TSK-117 | EP-12 | Reimbursement | PH2 | Story | Reimbursement Request Flow | Submit: amount, currency, category, receipt upload; 2-layer approval | Critical | 8 | TSK-031 | BE+FE | To Do
TSK-118 | EP-12 | Reimbursement | PH2 | Task | Finance Reimbursement Processing | Finance verifies receipt; records transfer; posts to ledger; notifies employee | Critical | 5 | TSK-117 | BE+FE | To Do
TSK-119 | EP-12 | Reimbursement | PH2 | Task | Reimbursement History | Employee views all reimbursement history; status tracking | High | 3 | TSK-117 | FE | To Do
TSK-120 | EP-12 | Reimbursement | PH2 | Sub-task | Duplicate Reimbursement Detection | Warn on same date+amount+category combination | Medium | 2 | TSK-117 | BE | To Do
EP-13 ▸ Procurement & Asset Register [4 tasks ¦ 21 story pts]
TSK-121 | EP-13 | Procurement & Asset Register | PH2 | Story | Procurement Request Flow | Submit: item, qty, est. price, reason; 2-layer approval; Finance confirms receipt | High | 8 | TSK-027 | BE+FE | To Do
TSK-122 | EP-13 | Procurement & Asset Register | PH2 | Task | Procurement Status Tracking | Status: Approved → In Process → Received; Finance confirms; notify requester | High | 5 | TSK-121 | BE+FE | To Do
TSK-123 | EP-13 | Procurement & Asset Register | PH2 | Task | Asset Register | Register assets: name, value, location, purchase date; link from procurement | Medium | 5 | TSK-121 | BE+FE | To Do
TSK-124 | EP-13 | Procurement & Asset Register | PH2 | Sub-task | Procurement to Finance Integration | Auto-create expense transaction in Finance when procurement is completed | High | 3 | TSK-121 | BE | To Do

## 🟦 PH3
PHASE 3 — GROWTH
Sales & Marketing, SP Automation, Executive Portal, Content
Task ID | Epic ID | Epic Name | Phase | Type | Title | Description | Priority | Story Pts | Dependencies | Role | Status
EP-14 ▸ Sales Leads & Funnel [9 tasks ¦ 46 story pts]
TSK-125 | EP-14 | Sales Leads & Funnel | PH3 | Story | Lead Management Module | CRUD leads: company, PIC, services, source, stage; assign + reassign | Critical | 13 | TSK-028 | BE+FE | To Do
TSK-126 | EP-14 | Sales Leads & Funnel | PH3 | Task | Lead Funnel Stages | 6-stage funnel: Prospect/Qualified/Proposal/Negotiation/Closed Won/Lost | Critical | 5 | TSK-125 | BE+FE | To Do
TSK-127 | EP-14 | Sales Leads & Funnel | PH3 | Task | Lead Stage Transition Rules | Stage rules: PO required for Won; reason required for Lost; stage regression reason | High | 5 | TSK-126 | BE | To Do
TSK-128 | EP-14 | Sales Leads & Funnel | PH3 | Task | Activity Log per Lead | Log: date, type (call/email/meeting), notes; history timeline view | High | 5 | TSK-125 | BE+FE | To Do
TSK-129 | EP-14 | Sales Leads & Funnel | PH3 | Task | Referral Tracking | Record referring employee; link to commission on Closed Won | High | 5 | TSK-125 | BE | To Do
TSK-130 | EP-14 | Sales Leads & Funnel | PH3 | Task | Direktur Closing Flow | Direktur marks Closed Won; no commission generated; tagged as Direktur-Driven | Critical | 5 | TSK-126 | BE+FE | To Do
TSK-131 | EP-14 | Sales Leads & Funnel | PH3 | Task | Lost Deal Re-engagement | Reopen Closed Lost lead; preserve full history; new stage tracking | Medium | 3 | TSK-126 | BE+FE | To Do
TSK-132 | EP-14 | Sales Leads & Funnel | PH3 | Sub-task | Lead Duplicate Detection | Warn on same company + service within 90 days | Medium | 2 | TSK-125 | BE | To Do
TSK-133 | EP-14 | Sales Leads & Funnel | PH3 | Sub-task | PO Upload & Finance Notification | Sales uploads PO on Closed Won; auto-notify Finance | Critical | 3 | TSK-126 | BE+FE | To Do
EP-15 ▸ Proposal Management [5 tasks ¦ 29 story pts]
TSK-134 | EP-15 | Proposal Management | PH3 | Story | Proposal Creation & Versioning | Create proposal linked to lead; scope/timeline/pricing; version history | Critical | 8 | TSK-125 | BE+FE | To Do
TSK-135 | EP-15 | Proposal Management | PH3 | Task | Proposal Approval Flow | Manager → GM/CLevel approval; blocks "sent" without approval | Critical | 5 | TSK-134 | BE+FE | To Do
TSK-136 | EP-15 | Proposal Management | PH3 | Task | Proposal PDF Export | Generate PDF with all proposal fields; version stamp; send-date record | High | 5 | TSK-134 | BE+FE | To Do
TSK-137 | EP-15 | Proposal Management | PH3 | Task | Payment Terms (Termin) Setup | Define invoice terms per project: % + trigger (milestone/date); Finance notif | Critical | 8 | TSK-134 | BE+FE | To Do
TSK-138 | EP-15 | Proposal Management | PH3 | Sub-task | Proposal Status Tracking | Status: Draft/In Review/Approved/Sent/Won/Lost; with timestamps | High | 3 | TSK-134 | BE | To Do
EP-16 ▸ Sales Targets & Reports [5 tasks ¦ 29 story pts]
TSK-139 | EP-16 | Sales Targets & Reports | PH3 | Story | Sales Target Setting | Manager sets individual targets; GM/CLevel sets dept target; monthly/quarterly | High | 8 | TSK-125 | BE+FE | To Do
TSK-140 | EP-16 | Sales Targets & Reports | PH3 | Task | Win Rate Calculation Engine | Win Rate = Closed Won / (Won + Lost); per salesperson; per service category | Critical | 5 | TSK-126 | BE | To Do
TSK-141 | EP-16 | Sales Targets & Reports | PH3 | Task | Sales Performance Report | Report: win rate, revenue, deal cycle, vs target; filter by period/salesperson | High | 8 | TSK-140 | BE+FE | To Do
TSK-142 | EP-16 | Sales Targets & Reports | PH3 | Task | Target vs Actual Tracking | Real-time progress bar per salesperson; mid-month <50% alert to manager | High | 5 | TSK-139 | BE+FE | To Do
TSK-143 | EP-16 | Sales Targets & Reports | PH3 | Sub-task | Direktur Deal Segmentation | Separate Direktur-Driven deals from team deals in all reports | High | 3 | TSK-130 | BE | To Do
EP-17 ▸ Warning Letter (SP) System [6 tasks ¦ 29 story pts]
TSK-144 | EP-17 | Warning Letter (SP) System | PH3 | Story | SP Manual Creation Flow | Operation creates SP manually; mandatory fields; GM/CLevel approval; digital ack | Critical | 8 | TSK-031 | BE+FE | To Do
TSK-145 | EP-17 | Warning Letter (SP) System | PH3 | Task | SP Sequence Enforcement | Enforce SP1→SP2→SP3 sequence; SP3 triggers layoff request to Direktur | Critical | 5 | TSK-144 | BE | To Do
TSK-146 | EP-17 | Warning Letter (SP) System | PH3 | Task | SP Employee Acknowledgment | SP shown in employee portal; digital acknowledgment required; 7-day escalation | Critical | 5 | TSK-144 | BE+FE | To Do
TSK-147 | EP-17 | Warning Letter (SP) System | PH3 | Task | SP History & Audit | Full SP history per employee; stored permanently; visible to Operation/GM | High | 3 | TSK-144 | BE+FE | To Do
TSK-148 | EP-17 | Warning Letter (SP) System | PH3 | Task | SP for Outsource (SP-O) Module | SP-O1/O2/O3 flow; Operation input after Sales reports client complaint | High | 5 | TSK-110 | BE+FE | To Do
TSK-149 | EP-17 | Warning Letter (SP) System | PH3 | Sub-task | SP Layoff Request Trigger | SP3 creates layoff request; routes to Direktur for approval; no auto-fire | Critical | 3 | TSK-145 | BE | To Do
EP-18 ▸ Executive Portal [6 tasks ¦ 41 story pts]
TSK-150 | EP-18 | Executive Portal | PH3 | Story | Executive Dashboard | Real-time KPI cards: People, Technology, Sales, Finance, Outsource | Critical | 13 | TSK-091 | BE+FE | To Do
TSK-151 | EP-18 | Executive Portal | PH3 | Task | EBITDA Dashboard | EBITDA calculation; margin %; per revenue stream; 12-month trend chart | High | 8 | TSK-091 | BE+FE | To Do
TSK-152 | EP-18 | Executive Portal | PH3 | Task | People Performance Overview | Bell curve distribution; dept avg; top/bottom performers; drill-down | High | 8 | TSK-080 | BE+FE | To Do
TSK-153 | EP-18 | Executive Portal | PH3 | Task | Operational KPIs Dashboard | Hiring fill rate; onboarding completion; payroll timeliness; reimbursement TAT | High | 5 | TSK-029 | BE+FE | To Do
TSK-154 | EP-18 | Executive Portal | PH3 | Task | Executive Portal Access Gate | Direktur Utama only; redirect all others to Employee Portal | Critical | 2 | TSK-003 | BE | To Do
TSK-155 | EP-18 | Executive Portal | PH3 | Sub-task | Dashboard Drill-down Navigation | Click on metric → navigate to source module with filter applied | Medium | 5 | TSK-150 | FE | To Do
EP-19 ▸ Broadcast, Events & Company Info [5 tasks ¦ 28 story pts]
TSK-156 | EP-19 | Broadcast, Events & Company Info | PH3 | Story | Broadcast Module | Create broadcast: rich text, image, file attach; targeted audience; schedule | High | 8 | TSK-057 | BE+FE | To Do
TSK-157 | EP-19 | Broadcast, Events & Company Info | PH3 | Task | Audience Targeting Engine | Target by: global, department, level, or combination; permission by sender level | High | 5 | TSK-156 | BE | To Do
TSK-158 | EP-19 | Broadcast, Events & Company Info | PH3 | Task | Event Management Module | Create event: title, datetime, location, description, audience; RSVP | High | 5 | TSK-057 | BE+FE | To Do
TSK-159 | EP-19 | Broadcast, Events & Company Info | PH3 | Task | RSVP & Event Reminder | Employees RSVP Attending/Not; organizer sees list; H-1 reminder auto-sent | Medium | 5 | TSK-158 | BE+FE | To Do
TSK-160 | EP-19 | Broadcast, Events & Company Info | PH3 | Task | News Feed (Berita Perusahaan) | Chronological feed of broadcasts per employee; filter by dept/global | Medium | 5 | TSK-156 | FE | To Do
EP-20 ▸ Resignation & Offboarding [6 tasks ¦ 24 story pts]
TSK-161 | EP-20 | Resignation & Offboarding | PH3 | Story | Resignation Submission Flow | Employee submits resign; 30-day notice validation; supervisor acknowledge | Critical | 5 | TSK-019 | BE+FE | To Do
TSK-162 | EP-20 | Resignation & Offboarding | PH3 | Task | Offboarding Checklist | Auto-create: asset return, handover, exit interview, clearance, final payroll | Critical | 5 | TSK-161 | BE+FE | To Do
TSK-163 | EP-20 | Resignation & Offboarding | PH3 | Task | Active Placement & PM Check on Resign | Block/warn if resigning employee has active outsource placement or is PM | Critical | 3 | TSK-161 | BE | To Do
TSK-164 | EP-20 | Resignation & Offboarding | PH3 | Task | Portal Access Revocation on Exit | Immediately revoke all access on last working day; invalidate sessions | Critical | 3 | TSK-019 | BE | To Do
TSK-165 | EP-20 | Resignation & Offboarding | PH3 | Task | Layoff Request & Approval Flow | Request layoff: 2-layer approval; offboarding same as resign; pesangon notes | Critical | 5 | TSK-031 | BE+FE | To Do
TSK-166 | EP-20 | Resignation & Offboarding | PH3 | Sub-task | Final Payroll Settlement | Trigger final prorated payroll on exit; link to Finance for processing | Critical | 3 | TSK-054 | BE | To Do

## 🟢 PH4
PHASE 4 — INTELLIGENCE
AI Features, Advanced Analytics, Digital Signature, Reports
Task ID | Epic ID | Epic Name | Phase | Type | Title | Description | Priority | Story Pts | Dependencies | Role | Status
EP-21 ▸ AI Action Items & SP Drafting [4 tasks ¦ 29 story pts]
TSK-167 | EP-21 | AI Action Items & SP Drafting | PH4 | Story | AI Sales Action Item Generator | AI generates contextual action items per lead per stage; accept/edit/ignore | High | 13 | TSK-126 | BE+AI | To Do
TSK-168 | EP-21 | AI Action Items & SP Drafting | PH4 | Task | AI SP Draft Generator | AI drafts SP letter from rating history; editable before approval | High | 8 | TSK-081 | BE+AI | To Do
TSK-169 | EP-21 | AI Action Items & SP Drafting | PH4 | Task | AI Service Unavailability Fallback | Graceful degradation when AI unavailable; show manual input option | Medium | 3 | TSK-167 | BE+FE | To Do
TSK-170 | EP-21 | AI Action Items & SP Drafting | PH4 | Sub-task | Action Item Tracking | Track accepted/edited/ignored action items; completion rate per sales | Medium | 5 | TSK-167 | BE+FE | To Do
EP-22 ▸ Digital Signature (BA & SP) [5 tasks ¦ 36 story pts]
TSK-171 | EP-22 | Digital Signature (BA & SP) | PH4 | Story | BA Digital Signature (Client Token) | Send unique token link to client PIC; signature UI; both parties sign; PDF final | Critical | 13 | TSK-105 | BE+FE | To Do
TSK-172 | EP-22 | Digital Signature (BA & SP) | PH4 | Task | Token Generation & Expiry | Unique token per BA per period; expiry handling; regenerate flow | Critical | 5 | TSK-171 | BE | To Do
TSK-173 | EP-22 | Digital Signature (BA & SP) | PH4 | Task | Client Signature Interface | No-login page via token; display BA detail; draw/type signature; confirm | Critical | 8 | TSK-171 | FE | To Do
TSK-174 | EP-22 | Digital Signature (BA & SP) | PH4 | Task | Client KPI Form via Token | Same token mechanism for client to rate outsource employee performance | High | 5 | TSK-108 | FE | To Do
TSK-175 | EP-22 | Digital Signature (BA & SP) | PH4 | Sub-task | Signed PDF Generation | Embed both digital signatures into BA PDF; store final version in system | Critical | 5 | TSK-173 | BE | To Do
EP-23 ▸ AI Executive Summary [5 tasks ¦ 39 story pts]
TSK-176 | EP-23 | AI Executive Summary | PH4 | Story | Monthly AI Executive Summary | Auto-generate narrative + chart summary at month start for previous month | High | 13 | TSK-150 | BE+AI | To Do
TSK-177 | EP-23 | AI Executive Summary | PH4 | Task | Data Aggregation for Summary | Pull all KPIs from all modules; structure for AI prompt engineering | High | 8 | TSK-176 | BE | To Do
TSK-178 | EP-23 | AI Executive Summary | PH4 | Task | AI Narrative Generation | Send aggregated data to AI; generate: achievements, risks, recommendations | High | 8 | TSK-177 | BE+AI | To Do
TSK-179 | EP-23 | AI Executive Summary | PH4 | Task | Executive Summary PDF Export | Export summary with charts as downloadable PDF; shareable link | High | 5 | TSK-176 | BE+FE | To Do
TSK-180 | EP-23 | AI Executive Summary | PH4 | Sub-task | On-demand Dept Summary | GM/CLevel can request AI summary for their department anytime | Medium | 5 | TSK-178 | BE+FE | To Do
EP-24 ▸ Data Migration & Import Tools [6 tasks ¦ 50 story pts]
TSK-181 | EP-24 | Data Migration & Import Tools | PH4 | Story | Bulk Import via Excel Template | Import employees, clients, org structure via Excel template; validation + error report | Critical | 13 | TSK-013 | BE+FE | To Do
TSK-182 | EP-24 | Data Migration & Import Tools | PH4 | Task | Import Validation Engine | Validate: required fields, duplicate NIK, dept existence, salary range | Critical | 8 | TSK-181 | BE | To Do
TSK-183 | EP-24 | Data Migration & Import Tools | PH4 | Task | Payroll History Import | Import historical pay slips per employee since joining; PDF generation | High | 8 | TSK-051 | BE | To Do
TSK-184 | EP-24 | Data Migration & Import Tools | PH4 | Task | Jira Project Import | Parse Jira export; map projects/epics/issues to IDEA project structure | High | 8 | TSK-073 | BE | To Do
TSK-185 | EP-24 | Data Migration & Import Tools | PH4 | Task | Rollback & Recovery Plan | Pre-cutover backup; rollback trigger; restore to pre-migration state | Critical | 8 | TSK-181 | BE+DevOps | To Do
TSK-186 | EP-24 | Data Migration & Import Tools | PH4 | Sub-task | Migration Progress Dashboard | Real-time import progress; error log; admin download error report | High | 5 | TSK-181 | FE | To Do
EP-25 ▸ Reporting & Analytics [6 tasks ¦ 47 story pts]
TSK-187 | EP-25 | Reporting & Analytics | PH4 | Story | Comprehensive Report Module | All reports: Finance, HR, Sales, Operations; filters; export PDF+Excel | High | 13 | TSK-098 | BE+FE | To Do
TSK-188 | EP-25 | Reporting & Analytics | PH4 | Task | HR Analytics Dashboard | Headcount trend; turnover rate; hire vs resign; dept distribution; tenure | High | 8 | TSK-013 | BE+FE | To Do
TSK-189 | EP-25 | Reporting & Analytics | PH4 | Task | Sales Analytics Dashboard | Pipeline value; conversion by stage; revenue forecast; team comparison | High | 8 | TSK-140 | BE+FE | To Do
TSK-190 | EP-25 | Reporting & Analytics | PH4 | Task | Finance KPI Widgets for Executive | Outstanding receivables; burn rate; EBITDA trend; cash runway estimate | High | 8 | TSK-150 | BE+FE | To Do
TSK-191 | EP-25 | Reporting & Analytics | PH4 | Task | System Audit Log Report | Admin views all critical action logs; filter by user/date/action type; export | High | 5 | TSK-011 | BE+FE | To Do
TSK-192 | EP-25 | Reporting & Analytics | PH4 | Sub-task | Scheduled Report Generation | Auto-generate and notify key reports at configured intervals (monthly/weekly) | Medium | 5 | TSK-187 | BE | To Do

## 🏃 Sprint Planning
SPRINT PLANNING — IDEA Internal Portal
Kickoff: 1 Jun 2026 · Sprint length: 2 minggu · Velocity target: 30-40 pts (solo+AI)
SPRINT 1 · 1 – 14 Jun 2026
🎯 Goal: Payroll engine end-to-end: attendance → calc → review → slip
Task ID | Epic | Title | Type | Priority | Pts | Status | Milestone
TSK-047 | EP-05 | Monthly Attendance Input by Operation | Task | Critical | 5 | Done | M1.4
TSK-048 | EP-05 | Payroll Calculation Engine | Story | Critical | 13 | Done | M1.4
TSK-049 | EP-05 | PPh 21 Manual Input per Employee | Task | Critical | 5 | Done | M1.4
TSK-050 | EP-05 | Payroll Review & Approval by GM/CLevel | Task | Critical | 5 | Done | M1.4
TSK-052 | EP-05 | Pay Slip History Access | Task | Critical | 3 | Done | M1.4
TSK-055 | EP-05 | Payroll Period Configuration | Task | High | 3 | Done | M1.4
TSK-056 | EP-05 | Payroll Duplicate Prevention | Task | Critical | 2 | Done | M1.4
|  |  |  | TOTAL: | 36
SPRINT 2 · 15 – 28 Jun 2026
🎯 Goal: M1.4 payroll variants (THR, prorated) + Alert Rules + M1.2 UI closure
Task ID | Epic | Title | Type | Priority | Pts | Status | Milestone
TSK-053 | EP-05 | THR Processing Module | Task | High | 5 | Done | M1.4
TSK-054 | EP-05 | Prorated Final Payroll (Exit) | Task | Critical | 5 | Done | M1.4
TSK-059 | EP-06 | Alert Rules Engine | Story | High | 8 | Done | M1.4
TSK-061 | EP-06 | Notification Retry & Failure Handling | Task | Medium | 3 | Done | M1.4
TSK-197 | EP-02 | Promotion UI Page (US-OP-012) | Story | High | 5 | Done | M1.2
TSK-198 | EP-02 | Mutation UI Page (US-OP-013) | Story | Medium | 5 | Done | M1.2
TSK-199 | EP-02 | PKWT Renewal Decision UI (US-OP-014) | Story | Critical | 5 | Done | M1.2
|  |  |  | TOTAL: | 36
SPRINT 3 · 29 Jun – 12 Jul 2026
🎯 Goal: M1.3 closure: hiring + onboarding (probation, welcome, CMS)
Task ID | Epic | Title | Type | Priority | Pts | Status | Milestone
TSK-034 | EP-03 | Offering Letter Generation | Story | Critical | 8 | Done | M1.3
TSK-036 | EP-03 | Internal Job Board | Task | Medium | 3 | Done | M1.3
TSK-037 | EP-03 | Duplicate Request Detection | Task | Medium | 2 | Done | M1.3
TSK-040 | EP-04 | Welcome Page for New Employees | Task | High | 5 | Done | M1.3
TSK-042 | EP-04 | H-3 Pre-join Preparation Alert | Task | High | 3 | Done | M1.3
TSK-043 | EP-04 | Account Activation on Join Date | Task | Critical | 3 | Done | M1.3
TSK-044 | EP-04 | Probation Assessment Flow | Story | High | 8 | Done | M1.3
TSK-045 | EP-04 | Company Info Portal (CMS) | Task | High | 5 | Done | M1.3
|  |  |  | TOTAL: | 37
SPRINT 4 · 13 – 26 Jul 2026
🎯 Goal: PH1 GATE Demo + sign-off — gerbang ke PH2
Task ID | Epic | Title | Type | Priority | Pts | Status | Milestone
demo-1 | — | Seed 10 dummy karyawan + 1 dept Teknologi full | Task | Critical | 2 | To Do | PH1 GATE
demo-2 | — | End-to-end smoke test: login → hiring → onboarding → payroll | Task | Critical | 3 | To Do | PH1 GATE
demo-3 | — | Bug-fix sweep (audit_frontend + audit_models + smoke run) | Task | High | 5 | To Do | PH1 GATE
demo-4 | — | PH1 GATE acceptance checklist (8 kriteria) | Story | Critical | 3 | To Do | PH1 GATE
demo-5 | — | Stakeholder sign-off prep: Dirut, GM Op, CTO | Task | Critical | 2 | To Do | PH1 GATE
demo-6 | — | PH2 M2.1 sprint planning + backlog refinement | Task | Medium | 2 | To Do | Plan
|  |  |  | TOTAL: | 17